## APR 2018-19
2018/2019 DRAFT ANNUAL PERFORMANCE REPORT
NAME OF MUNICIPALITY: UTHUKELA DISTRICT MUNICIPALITY
IDP / SDBIP NO. | OBJECTIVE | STRATEGIES | NO | INDICATORS | Unit of Measure | Ward No. | 2017/2018 |  |  | ANNUAL TARGET | Annual Actual | Achieved/Not Achieved | Reason for Variance | Corrective Measure | Responsible Dept | Budget | Portfolio of Evidence
[7 empty] | Demand | Baseline | Backlog
KPA 1: MUNICIPAL TRANFORMATION AND INSTITUTIONAL DEVELOPMENT
MTID01 | To ensure functional Performance Management System implemented | Implementation of PMS Policy & Framework | 1 | Date of review and adoption of PMS Policy and Proceduaral Framework by Council by 30/06/2019 | Date | n/a | Adoption of PMS Policy and Proceduaral Framework by 30/05/2019 | PMS Policy and Proceduaral Framework reviewed and adopted on 18/05/2018 | n/a | Adoption of PMS Policy and Proceduaral Framework by 30/05/2019 | PMS Policy and Proceduaral Framework was reviewed and adopted on the 30/05/2019 | Achieved | n/a | n/a | Office of the MM | OPEX | Council resolution and copy of the PMS Policy and Proceduaral Framework
MTID02 |  |  | 2 | Number of quarterly performance management reports submitted to Council by 30/06/2019 | Number | n/a | Four (4) quarterly performance management reports submitted to Council by 30/06/2019 | Four (4) quarterly performance management reports submitted to Council by 30/06/2018 | n/a | Four (4) quarterly performance management reports submitted to Council by 30/06/2019 | Four (4) quarterly performance management reports submitted to Council by 30/06/2019 | Achieved | n/a | n/a | Office of the MM | OPEX | Council resolutions and Quarterly reports
MTID03 |  |  | 3 | Date of submission of Mid-Year Performance Report to the Mayor and Treasuries by 25/01/2019 | Date | n/a | Submission of Mid-Year Performance Report to the Mayor and Treasuries by 25/01/2019 | Submission of Mid-Year Performance Report to the Mayor and Treasuries by 25/01/2018 | n/a | Submission of Mid-Year Performance Report to the Mayor and Treasuries by 25/01/2019 | Mid-Year Performance Report was submitted to the Mayor on the 17/01/2019 and Treasuries by 25/01/2019 | Achieved | n/a | n/a | Office of the MM | OPEX | Proof of submission and Mid-Year Performance Report
MTID04 |  |  | 4 | Date of submission of unaudited Annual Performance Report to the Auditor-Genral by 31/08/2019 | Date | n/a | Submission of unaudited Annual Performance Report to the Auditor-Genral by 31/08/2019 | Submission of unaudited Annual Performance Report to the Auditor-Genral by 31/08/2018 | n/a | Submission of unaudited Annual Performance Report to the Auditor-Genral by 31/08/2019 | Unaudited Annual Performance Report were submitted to the Auditor-Genral by 31/08/2019 | Achieved | n/a | n/a | Office of the MM | OPEX | Proof of submission and Annual Performance Report
MTID05 |  |  | 5 | Date table of Annual Report to Council by 31/01/2019 | Date | n/a | Tabling of Annual Report to Council by 31/01/2019 | Annual Report tabled to Council by 26/01/2018 | n/a | Tabling of Annual Report to Council by 31/01/2019 | Annual Report was tabled to Council on the 31/01/2019 | Achieved | n/a | n/a | Office of the MM | OPEX | Council resolution
MTID06 |  |  | 6 | Number of section 54/56 managers ‘performance reviews conducted per financial year |  |  | 2 Performance reviews conducted by 30/06/2019 | 2 Performance reviews conducted by 30/06/2018 | n/a | 2 Performance reviews conducted by 30/06/2019 | 2 Performance reviews were conducted by 30/06/2019 | Achieved | n/a | n/a | Office of the MM | OPEX | Signed Assessment Reports
MTID07 | To ensure fucntional risk management | Review and adopt risk management fraework | 7 | Date of review and adoption of risk management framework by Council by 30/06/2019 | Date | n/a | Review and adoption of risk management framework by Council by 30/06/2019 | Risk management framework reviewed and adopted by Council by 30/06/2018 | n/a | Review and adoption of risk management framework by Council by 30/06/2019 | Risk management framework was reviewed and adopted by Council on the 30/06/2019 | Achieved | n/a | n/a | Office of the MM | OPEX | Council resolution and risk management framework
MTID08 | To Improve organisational Capacity | Review of organisational structure | 8 | Number of organizational structures reviewed and adopted by Council by 30/06/2019 | Number | n/a | One (1) organizational structures reviewed and adopted by Council by 30/06/2019 | One (1) organizational structures reviewed and adopted by Council by 30/06/2018 | n/a | One (1) organizational structures reviewed and adopted by Council by 30/06/2019 | One (1) organizational structures reviewed and adopted by Council by 30/06/2019 | Achieved | n/a | n/a | Corporate Services | OPEX | Council Resoution and copy of the organisational structure
MTID09 |  | Employment equity plan adopted | 9 | Number of people from employment equity target groups employed in the three highest levels of management in compliance with approved equity plan by 30/06/2019 | Number | n/a | Two (2) people from employment equity target groups employed in the three highest levels of management in compliance with approved equity plan 30/06/2019 | n/a | n/a | Two (2) people from employment equity target groups employed in the three highest levels of management in compliance with approved equity plan by 30/06/2019 | Two (2) people from employment equity target groups employed in the three highest levels of management in compliance with approved equity plan by 30/06/2019 | Achieved | n/a | n/a | Corporate Services | OPEX | Employment Equity Plan and appointment letters
MTID10 |  | Implementation of Workplace Skills Plan | 10 | Percentage of budget spent in the implementation of Workplace Skills Plan by 30/06/2019 | Percentage | n/a | Hundred (100%) of budget spent in the implementation of Workplace Skills Plan by 30/06/2019 | Sixty (60%) of budget spent in the implementation of Workplace Skills Plan by 30/06/2019 | n/a | Hundred (100%) of budget spent in the implementation of Workplace Skills Plan by 30/06/2019 | Hundred (100%) of the implementation of Workplace Skills Plan budget was spent by 30/06/2019 | Achieved | n/a | n/a | Corporate Services | OPEX | Signed training reports
MTID11 | To ensure an effective and efficient HR systems that addresses Human resources within the municipality | Review and adotion of HR related policies | 11 | Date to review and adopt HR related policies by Council by 30/06/2019 | Date | n/a | Review and adoption of HR related policies by Council by 30/06/2019 | HR related policies reviewed and adopted by Council by 30/04/2018 | n/a | Review and adoption of HR related policies by Council by 30/06/2019 | Review and adoption of HR related policies were reviewed and adopted by Council on the 30/05/2019 | Achieved | n/a | n/a | Corporate Services | OPEX | HR related policies & Council Resolution
MTID12 | To ensure effective and efficient internal and external communication strategy. | Review and adoption of Communication Strategy | 12 | Date of review and adotion of communication strategy by Council by 30/06/2019 | Date | n/a | Review and adotion of communication strategy by Councl by 30/06/2019 | Communication strategy reviewed and adopted by Councl by 30/06/2018 | n/a | Review and adotion of communication strategy by Councl by 30/06/2019 | Communication strategy was reviewed and adopted by Council on the 28/06/2019 | Achieved | n/a | n/a | Office of the MM | OPEX | Communication Strategy & Council Resolution
MTID13 | To report & monitor Service Delivery | Submission of quarterly reports to Cogta | 13 | Number of B2B Quarterly Performance Reports and support plan submitted to Provincial Cogta by 30/06/2019 | Number | n/a | Four (4) 4B2B Quarterly Performance Reports and support plan submitted to Provincial Cogta by 30/06/2019 | Four (4) 4B2B Quarterly Performance Reports and support plan submitted to Provincial Cogta by 30/06/2019 | n/a | Four (4) 4B2B Quarterly Performance Reports and support plan submitted to Provincial Cogta by 30/06/2019 | Four (4) 4B2B Quarterly Performance Reports and support plan submitted were submitted to Provincial Cogta by 30/06/2019 | Achieved | n/a | n/a | Office of the MM | OPEX | B2B Report, Proof of submission
MTID14 | To improve the municipal Audit opinion | Effective Audit and Performance Committee | 14 | Number of Audit and Performance Committee meetings held by 30/06/2019 | Number | n/a | Four (4) Audit and Performance Committee meetings held by 30/06/2019 | Six (6) Audit and Performance Committee meetings held by 30/06/2019 | n/a | Four (4) Audit and Performance Committee meetings held by 30/06/2019 | Four (4) Audit and Performance Committee meetings were held by 30/06/2019 | Achieved | n/a | n/a | Office of the MM | OPEX | Notice, minutes & attendance registers
MTID15 |  | Oversight meetings held | 15 | Number of MPAC meetings convened by 30/06/2019 | Number | n/a | Four (4) MPAC meetings convened by 30/06/2019 | Eight (8) MPAC meetings convened by 30/06/2019 | n/a | Four (4) MPAC meetings convened by 30/06/2019 | Four (4) MPAC meetings were convened by 30/06/2019 | Achieved | n/a | n/a | Office of the MM | OPEX | Notice, minutes & attendance registers
KPA2: BASIC SERVICE DELIVERY
IDP / SDBIP NO. | OBJECTIVE | STRATEGIES | NO | INDICATORS | Unit of Measure | Ward No. | 2017/2018 |  |  | ANNUAL TARGET | Annual Actual | Achieved/Not Achieved | Reason for Variance | Corrective Measure | Responsible Dept | Budget | Portfolio of Evidence
[7 empty] | Demand | Baseline | Backlog
BSD01 | To eradicate water backlogs within a district | Provide portable water to households | 1 | Number of new households provided with water connections by 30/06/2019 | Number | Various | Six Hundred and Eighty Nine (689) of new households provided with water connections by 30/06/2019 | Two Hundred and Thity (230) of new households provided with water connections by 30/06/2018 | Four Hundred and Fifty Nine (459) of new households provided with water connections by 30/06/2019 | Six Hundred and Eighty Nine (689) of new households provided with water connections by 30/06/2019 | 689 of new households provided with water connections by 30/06/2019 | Achieved | n/a | n/a | Water Sanitation & Technical Department | CACPEX | Progress reports and Beneficiary list
BSD02 | To provide infrastructure and sustainable basic services | Provide community water supply | 2 | Kilometres of reticulation lines constructed at Ntambahlophe Phase 13 community water supply by 30/06/2019 | Kilometres | 12 | 15 Kilometres of reticulation lines constructed at Ntabamhlophe Phase 13 community water supply by 30/06/2019 | n/a | 15 Kilometres of reticulation lines constructed at Ntabamhlophe Phase 13 community water supply by 30/06/2019 | 15 Kilometres of reticulation lines constructed at Ntabamhlophe Phase 13 community water supply by 30/06/2019 | 14 780 Kilometres of reticulation lines constructed at Ntabamhlophe Phase 13 community water supply by 30/06/2019 | Not Achieved | There was additional scope of works wich reverted to the access road and retaining walls being built first | The Construction of access road and retaining walls was achieved now the contractor is busy with the construction of the reservoir. | Water Sanitation & Technical Department | R11 000 000.00 | Signed progress reports
BSD03 |  |  | 3 | Numner of standpipes installed in Ntabamhlophe Phase 13 community water supply by 30/06/2019 | Number | 12 | New Indicator | New Indicator | New Indicator | Thity Nine (39) standpipes installed in Ntabamhlophe phase 13 community water supply by 30/06/2019 | 44 standpipes installed in Ntabamhlophe phase 13 community water supply by 30/06/2019 | Achieved | n/a | n/a | Water, Sanitation & Technical Services |  | Signed progress reports
BSD04 |  |  | 4 | Number of concrete reinforce reservoirs constructed in Ntabamhlophe phase 13 community water supply by 30/06/2019 | Number | 12 | 1concrete reinforce reservoir constructed in Ntabamhlophe phase 13 community water supply by 30/06/2019 | n/a | 1concrete reinforce reservoir constructed in Ntabamhlophe phase 13 community water supply by 30/06/2019 | 1concrete reinforce reservoir constructed in Ntabamhlophe phase 13 community water supply by 30/06/2019 | 0 concrete reinforce reservoir constructed in Ntabamhlophe phase 13 community water supply by 30/06/2019 | Not Achieved | There was additional scope of works wich reverted to the access road and retaining walls being built first | The Construction of access road and retaining walls was achieved now the contractor is busy with the construction of the reservoir. | Water, Sanitation & Technical Services |  | Signed progress reports
BSD05 |  |  | 5 | Kilometres of Estcourt Industrial pepeline constructed by 30/06/2019 | Kilometres | 17 | 9 Kilometres of Estcourt Industrial pepeline constructed by 30/06/2019 | n/a | 9 Kilometres of Estcourt Industrial pepeline constructed by 30/06/2019 | 9 Kilometres of Estcourt Industrial pepeline constructed by 30/06/2019 | 1 Kilometres of Estcourt Industrial pepeline constructed by 30/06/2019 | Not Achieved | The Local Bussiness Forum stopped works, | ISD intervened and The Project will continue in the next financial year | Water, Sanitation & Technical Services | R29 000 000.00 | Signed progress reports
BSD06 |  |  | 6 | Kilometres of reticulation line constructed at Bhekuzulu/Phangweni Phases 1and 2 by 30/06/2019 | Kilometres | 1&6 | 106.45 kilometres of reticulation line constructed at Bhekuzulu/Phangweni Phases 1and 2 by 30/06/2019 | 72 kilometres of reticulation line constructed at Bhekuzulu/Phangweni Phases 1and 2 by 30/06/2018 | 34,45 Kilometres of reticulation line constructed at Bhekuzulu/Phangweni Phases 1and 2 by 30/06/2019 | 114,5 Kilometres of reticulation line constructed at Bhekuzulu/Phangweni Phases 1and 2 by 30/06/2019 | 114.5 KM Kilometres of reticulation line constructed at Bhekuzulu/Phangweni Phases 1and 2 by 30/6/2019 | Achieved | n/a | n/a | Water, Sanitation & Technical Services | R18 000 000.00 | Signed progress reports
BSD07 |  |  | 7 | Number of households connections made at Bhekuzulu/Phangweni Phases 1 and 2 by 30/06/2019 | Number | 1&6 | Six Hundred and Eighty Nine (689) of households connections made at Bhekuzulu/Phangweni Phases 1 and 2 by 30/06/2019 | Two Hundred and Thity (230) of households connections made at Bhekuzulu/Phangweni Phases 1 and 2 by 30/06/2018 | Four Fifty Nine (459) of households connections made at Bhekuzulu/Phangweni Phases 1 and 2 by 30/06/2019 | Six Hundred and Eighty Nine (689) of households connections made at Bhekuzulu/Phangweni Phases 1 and 2 by 30/06/2019 | Six Hundred and Eighty Nine (689) of new households provided with water connections by 30/06/2019 | Achieved | n/a | n/a | Water, Sanitation & Technical Services |  | Signed progress reports and beneficiary list
BSD08 |  |  | 8 | Kilometres of reticulation pipeline installed at Phase 1 of Wembezi Water Concservation Demand Management by 30/06/2019 | Kilometres | 9 | 15 Kilometres of reticulation pipeline installed at Phase 1 of Wembezi Water Concservation Demand Management by 30/06/2019 | n/a | 15 Kilometres of reticulation pipeline installed at Phase 1 of Wembezi Water Concservation Demand Management by 30/06/2019 | 2 Kilometres of reticulation pipeline installed at Phase 1 of Wembezi Water Concservation Demand Management by 30/06/2019 | 0 Kilometres of reticulation pipeline installed at Phase 1 of Wembezi Water Concservation Demand Management by 30/06/2019 | Not Achieved | There were delays in issuing of health and Safety Permit | The Construction will continue in the next financial year | Water, Sanitation & Technical Services | R18 000 000.00 | Signed progress reports
BSD09 |  |  | 9 | Kilometres of bulk lines constructed in Bhekuzulu Phase 5 by 30/06/2019 | Kilometres | 2&3 | Two (2) kilometres of bulk lines constructed in Bhekuzulu phase 5 by 30/06/2019 | n/a | Two (2) kilometres of bulk lines constructed in Bhekuzulu phase 5 by 30/06/2019 | Two (2) kilometres of bulk lines constructed in Bhekuzulu phase 5 by 30/06/2019 | 0,5 Kilometres of bulk lines constructed in Bhekuzulu phase 5 by 30/06/2019 | Not Achieved | service provider failed to achieve tasks due to non perfomance and delays on the material needed. | The Contractor has procured all the necessary material needed and a revised programme was submitted. | Water, Sanitation & Technical Services | R29 000 000.00 | Signed progress reports
BSD10 |  |  | 10 | Kilometres of remedial works to the existing pipeline in Bhekuzulu phase 5 constructed by 30/06/2019 | Kilometres | 2&3 | 6,8 kilometres of remedial works to the existing pripelines in Bhekuzulu phase 5 constructed by 30/06/2019 | 0, 7 kilometres of remedial works to the existing pripelines in Bhekuzulu phase 5 constructed by 30/06/2018 | 6 kilometres of remedial works to the existing pripelines in Bhekuzulu phase 5 constructed by 30/06/2019 | 6 Kilometres of remedial works to the existing pipelines in Bhekuzulu phase 5 constructed by 30/06/2019 | 3 kilometres of remedial works to the existing pripelines in Bhekuzulu phase 5 constructed by 30/06/2019 | Not Achieved | service provider failed to achieve tasks due to non perfomance and delays on the material needed. | The Contractor has procured all the necessary material needed and a revised programme was submitted. | Water, Sanitation & Technical Services |  | Signed progress reports
BSD11 |  |  | 11 | Number of households provided with VIP toilets in Bergiville sanitation project by 31/03/2019 | Number | 5 | 531 households provided with VIP toilets in Bergiville sanitation project by 31/03/2019 | n/a | 531 households provided with VIP toilets in Bergiville sanitation project by 31/03/2019 | 531 households provided with VIP toilets in Bergiville sanitation project by 31/03/2019 | 531 households provided with VIP toilets in Bergiville sanitation project by 31/03/2019 | Achieved | n/a | n/a | Water, Sanitation & Technical Services | R5 000 000.00 | Signed progress reports
BSD12 |  |  | 12 | Kilometers of Reticulation constructed at Kwanobamba/Esitendeni Phase 1A | Kilometres |  | 3,8 km Kilometers of Reticulation constructed at Kwanobamba/Esitendeni Phase 1A by 30 June 2019 | New Indicator | 3,8 Kilometers of Reticulation constructed at Kwanobamba/Esitendeni Phase 1A by 30 June 2019 | 3,8 km Kilometers of Reticulation constructed at Kwanobamba/Esitendeni Phase 1A by 30 June 2019 | 3,8 Kilometers of Reticulation constructed at Kwanobamba/Esitendeni Phase 1A by 30 June 2019 | Achieved | n/a | n/a | Water, Sanitation & Technical Services | n/a | Signed progress reports
BSD13 |  |  | 13 | No of pump station refurbished at Ekuvukeni / Rising main and Booster Pump Station | Number |  | One pump refurbished at Ekuvukeni / Rising main and Booster Pump Station by 30 June 2019 | New Indicator | One pump refurbished at Ekuvukeni / Rising main and Booster Pump Station by 30 June 2019 | One pump refurbished at Ekuvukeni / Rising main and Booster Pump Station by 30 June 2019 | Zero pump refurbished at Ekuvukeni / Rising main and Booster Pump Station by 30 June 2019 | Not Achieved | Underground water seepage on excavation of watery recovery sump was reported | the underground water seepage was resolved and now the construction is in progress. | Water, Sanitation & Technical Services |  | Signed progress reports
BSD14 |  |  | 14 | KM's of Bulk Line at Ekuvukeni -Refurbishment of the Oliphant WTW | Kilometres |  | 11 km KM's of Bulk Line at Ekuvukeni -Refurbishment of the Oliphant WTW by 30/June/2019 | New Indicator | 11 km KM's of Bulk Line at Ekuvukeni -Refurbishment of the Oliphant WTW by 30/June/2019 | 11 km KM's of Bulk Line at Ekuvukeni -Refurbishment of the Oliphant WTW by 30/June/2019 | 0,76 km of Bulk Line at Ekuvukeni -Refurbishment of the Oliphant WTW by 30/June/2019 | Not Achieved | Underground water seepage on excavation of watery recovery sump was reported | the underground water seepage was resolved and now the construction is in progress. | Water, Sanitation & Technical Services |  | Signed progress reports
BSD15 |  |  | 15 | No of Spring Protection and Appurtenant works completed District wide | Number |  | 38 Spring Protected and Appurtenant works completed District wide by 30/06/2019 | New Indicator | 38 Spring Protected and Appurtenant works completed District wide by 30/06/2019 | 38 Spring Protected and Appurtenant works completed District wide by 30/06/2019 | 38 Spring Protected and Appurtenant works completed District wide by 30/06/2019 | Achieved | n/a | n/a | Water, Sanitation & Technical Services |  | Signed progress reports
BSD16 |  | Implement effective water quality monitoring program | 16 | Number of water treatment plants monitred by 30/06/2019 | Number | Various | Forteen (14) water treatment plants monitored by 30/06/2019 | New Indicator | Forteen (14) water treatment plants monitored by 30/06/2018 | Forteen (14) water treatment plants monitored by 30/06/2019 | Forteen (14) water treatment plants monitored by 30/06/2019 | Achieved | n/a | n/a | Municipal Health and Water Service Authority |  | Signed progress reports
BSD17 |  |  | 17 | Number of waste water treatment works monitored by 30/06/2019 | Number | Various | Nine (9) waste water treatment works monitored by 30/06/2019 | New Indicator | n/a | Nine (9) waste water treatment works monitored by 30/06/2019 | Nine (9) waste water treatment works monitored by 30/06/2019 | Achieved | n/a | n/a | Municipal Health and Water Service Authority | OPEX | Signed reports
BSD18 |  | Monitor food selling outlets compliance | 18 | Number of food handling premises inspected by 30/06/2019 | Number | All | One Thousand and Eight (1008) food handling premises inspected by 30/06/2019 | One Thousand and Eight (1008) food handling premises inspected by 30/06/2018 | n/a | 864 food handling premises inspected by 30/06/2019 | 925 food handling premises inspected by 30/06/2019 | Achieved | n/a | n/a | Municipal Health and Water Service Authority | OPEX | Signed reports
BSD19 |  | Provide community water supply | 19 | Kilometers of Reticulation constructed at Kwanobamba/Esitendeni Phase 1B | Kilometres |  | 3,8 km Kilometers of Reticulation constructed at Kwanobamba/Esitendeni Phase 1B by 30 June 2019 | New Indicator | 3,8 Kilometers of Reticulation constructed at Kwanobamba/Esitendeni Phase 1B by 30 June 2019 | 3,8 km Kilometers of Reticulation constructed at Kwanobamba/Esitendeni Phase 1B by 30 June 2019 | 3,8 Kilometers of Reticulation constructed at Kwanobamba/Esitendeni Phase 1B by 30 June 2019 | Achieved | n/a | n/a | Water, Sanitation & Technical Services | n/a | Signed progress reports
KPA3: LOCAL ECONOMIC DEVELOPMENT
IDP / SDBIP NO. | OBJECTIVE | STRATEGIES | NO | INDICATORS | Unit of Measure | Ward No. | 2017/2018 |  |  | ANNUAL TARGET | Annual Actual | Achieved/Not Achieved | Reason for Variance | Corrective Measure | Responsible Dept | Budget | Portfolio of Evidence
[7 empty] | Demand | Baseline | Backlog
LED01 | To enhance the Uthukela Local Economic Development | LED policy reviewed | 1 | Date of review and adoption of LED strategy by Council 30/06/2019 | Date | District -wide | Review and adoption of LED strategy by Council by 30/06/2019 | Review and adoption of LED strategy by Council by 30/06/2019 | n/a | Review and adoption of LED strategy by Council by 30/06/2019 | LED Strategy was not reviewed and adopted by council | Not Achieved | Due to budget constrains | Request for budget allocation to appoint service provider to assist in this regar | Social and Economic Services | OPEX | Council Resolution and LED strategy
LED02 | To Increase Job opportunities | Creation of job opportunities | 2 | Number of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2019 | Number | District -wide | 3200 of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2020 | 1053 of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2019 | 2147 of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2019 | 2652 of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2020 | 894 of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2020 | Not Achieved | Budget Allocation was for 894 beneficiaries only | Budget Allocation was for 894 beneficiaries only | Water, Sanitation & Technical Services/Social & Economic Services | R 6 200 000.00 | Signed reports
LED03 | To improve intergovernmental relations | Convene district LED/Tourism Forum meetings | 3 | Number of fucntional disrtict LED/Tourism forums 30/06/2019 | Number | n/a | One (1) fucntional district LED/Tourism and planning forum by 30/06/2019 | One (1) fucntional district LED/Tourism and planning forum by 30/06/2018 | n/a | One (1) fucntional district LED/Tourism and planning forum by 30/06/2019 | One (1) fucntional district LED/Tourism and planning forum by 30/06/2019 | Achieved | n/a | n/a | Social and Economic Services | OPEX | Signed reports
KPA 4: GOOD GOVERNANCE & PUBLIC PARTICIPATION
IDP / SDBIP NO. | OBJECTIVE | STRATEGIES | NO | INDICATORS | Unit of Measure | Ward No. | 2017/2018 |  |  | ANNUAL TARGET | Annual Actual | Achieved/Not Achieved | Reason for Variance | Corrective Measure | Responsible Dept | Budget | Portfolio of Evidence
[7 empty] | Demand | Baseline | Backlog
zxserg44e | To ensure good and effective governance | Participate the IGR Structures | 4 | Percentage of IGR Structures meetings coordinated by 30/06/2019 | Percentage | n/a | Hundred (100%) of IGR Structures meetings coordinated by 30/06/2019 | Hundred (100%) of IGR Structures meetings coordinated by 30/06/2019 | n/a | Hundred (100%) of IGR Structures meetings coordinated by 30/06/2019 | Hundred (100%) of IGR Structures meetings coordinated by 30/06/2019 | Achieved | n/a | n/a | Corporate Services | OPEX | Notice, minutes & attendance registers
GGPP02 | To promote the interest of designated groups | Participate in the annual programmes | 5 | Number of Special Programmes targeting designated groups co-ordinated and participating in within the district by 30/06/2019 | Number | All | Seven (7) Special Programmes targeting designated groups co-ordinated and participating in within the district by 30/06/2019 | Seven (7) Special Programmes targeting designated groups co-ordinated and participating in within the district by 30/06/2019 | n/a | Seven (7) Special Programmes targeting designated groups co-ordinated and participating in within the district by 30/06/2019 | Seven (7) Special Programmes targeting designated groups co-ordinated and participating in within the district by 30/06/2019 | Achieved | n/a | n/a | Office of the MM | OPEX | Signed Reports
KP5: MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
IDP / SDBIP NO. | OBJECTIVE | STRATEGIES | NO | INDICATORS | Unit of Measure | Ward No. | 2017/2018 |  |  | ANNUAL TARGET | Annual Actual | Achieved/Not Achieved | Reason for Variance | Corrective Measure | Responsible Dept | Budget | Portfolio of Evidence
[7 empty] | Demand | Baseline | Backlog
MFVM01 | To ensure legally sound financial viability and management | Timeous financial reporting and management | 1 | Percentange of MIG Expenditure by 30/06/2019 | Percentage | n/a | Hundred (100%) of MIG expenditure by 30/06/2019 | Hundred (100%) of MIG expenditure by 30/06/2018 | n/a | Hundred (100%) of MIG expenditure by 30/06/2019 | Awaiting Financial Projections |  |  |  | Water, Sanitation & Technical Services | MIG | Grant exenditure report and proof of payments
MFVM02 |  |  | 2 | Percentange of annual allocation to free basic services spent by 30/06/2019 | Percentage | n/a | Hundred (100%) of annual allocation to free basic services spent by 30/06/2019 | Hundred (100%) of annual allocation to free basic services spent by 30/06/2018 | n/a | Hundred (100%) of annual allocation to free basic services spent by 30/06/2019 | Awaiting Financial Projections |  |  |  | Budget & Treasury Office | OPEX | Signed reports
MFVM03 |  |  | 3 | Percentage of operating budget spent by 30/06/2019 | Percentage | n/a | Hundred (100%) of operating budget spent by 30/06/2019 | Hundred (100%) of operating budget spent by 30/06/2018 | n/a | Hundred (100%) of operating budget spent by 30/06/2019 | Awaiting Financial Projections |  |  |  | Budget & Treasury Office | OPEX | Signed reports
MFVM04 |  |  | 4 | Percentange of capital budget spent by 30/06/2019 | Percentage | n/a | Hundred (100%) of capital budget spent by 30/06/2019 | Hundred (100%) of capital budget spent by 30/06/2018 | n/a | Hundred (100%) of capital budget spent by 30/06/2019 | Awaiting Financial Projections |  |  |  | Budget & Treasury Office | CAPEX | Signed reports
MFVM05 |  |  | 5 | Percentange of repairs and maintenance spent by 30/06/2019 | Percentage | n/a | Hundred (100%) of repairs and maintenance spent by 30/06/2019 | Hundred (100%) of repairs and maintenance spent by 30/06/2018 | n/a | Hundred (100%) of repairs and maintenance spent by 30/06/2019 | Awaiting Financial Projections |  |  |  | Budget & Treasury Office | OPEX | Signed reports
MFVM06 |  |  | 6 | Ratio on financial viability in terms of debt coverage by 30/06/2019 | Ratio | n/a | 1:03 | 1:03 | n/a | 1:03 | Awaiting Financial Projections |  |  |  | Budget & Treasury Office | OPEX | Signed reports
MFVM07 |  |  | 7 | Ratio on financial viability in terms of cost coverage by 30/06/2019 | Ratio | n/a | 1:02 | 1:02 | `n/a | 1:02 | Awaiting Financial Projections |  |  |  | Budget & Treasury Office | OPEX | Signed reports
MFVM08 |  |  | 8 | Ratio on financial viability in terms of outstanding service debtors to revenue by 30/06/2019 | Ratio | n/a | 1:02 | 1:02 | n/a | 1:02 | Awaiting Financial Projections |  |  |  | Budget & Treasury Office | OPEX | Signed reports
MFVM09 |  |  | 9 | Date of approval of 2018/19 budget by 31/05/2019 | Date | n/a | Approval of 2019/20 budget by 31/05/2019 | Approval of 2019/20 budget by 31/05/2018 | n/a | Approval of 2019/20 budget by 31/05/2019 | Awaiting Financial Projections |  |  |  | Budget & Treasury Office | OPEX | Council resolution
MFVM10 |  |  | 10 | Date of submission of credble Annual Financial Statements to the Auditor-Genral by 31/08/2018 | Date | n/a | Submission of credble Annual Financial Statements to the Auditor-Genral by 31/08/2018 | Credble 2016/17 Annual Financial Statements submitted to the Auditor-Genral by 31/08/2017 | n/a | Submission of credble Annual Financial Statements to the Auditor-Genral by 31/08/2018 | Awaiting Financial Projections |  |  |  | Budget & Treasury Office | OPEX | Proof of submission and Annual Financial Statements
MFVM11 |  |  | 11 | Percentange of functional bid committees by 30/06/2019 | Percentage | n/a | Hundred (100%) of functional bid committees by 30/06/2019 | Hundred (100%) of functional bid committees by 30/06/2018 | n/a | Hundred (100%) of functional bid committees by 30/06/2019 | Awaiting Financial Projections |  |  |  | Budget & Treasury Office | OPEX | SCM reports
MFVM12 | To improve audit opinion | Implement an audit action plan | 12 | Percentage of audit queries raised by the Auditor-General addressed by 30/06/2019 | Percentage | n/a | Hundred (100%) of audit queries raised by the Auditor-General addressed by 30/06/2019 | Hundred (100%) of audit queries raised by the Auditor-General addressed by 30/06/2018 | n/a | Hundred (100%) of audit queries raised by the Auditor-General addressed by 30/06/2019 | Awaiting Financial Projections |  |  |  | All Departments | OPEX | Audit action plan and dashboard report
KPA 6: CROSS CUTTING ISSUES
IDP / SDBIP NO. | OBJECTIVE | STRATEGIES | NO | INDICATORS | Unit of Measure | Ward No. | 2017/2018 |  |  | ANNUAL TARGET | Annual Actual | Achieved/Not Achieved | Reason for Variance | Corrective Measure | Responsible Dept | Budget | Portfolio of Evidence
[7 empty] | Demand | Baseline | Backlog
CCI01 | To improved implementation of policies and by-laws | Adopted estates bylaws | 1 | Number of by-laws reviewed and adopted by Council by 30/06/2019 | Number | All | Seven (7) by-laws reviewed and adopted by Council by 30/06/2019 | n/a | Seven (7) by-laws reviewed and adopted by Council by 30/06/2019 | Seven (7) by-laws reviewed and adopted by Council by 30/06/2019 | 0 by-laws reviewed and adopted by Council by 30/06/2019 | Not Achieved | The Bylaws have been sumitted for translation and promulgation | The bylaws with be adopted by council once the translation and promulgation has been completed | Corporate Services | OPEX | Council resolutions, copies of advertisements and copy of the by-law document
CCI02 | Efficient & Credible Stratgic & Spatial Municipal Planning | Revision of a Credible Intergrated Development Plan | 2 | Date of review and adoption of credible integrated development planning by Council by 31/05/2019 | Date | n/a | Review and adoption of credible integrated development planning by Council by 30/06/2019 | Credible integrated development planning reviewed and adopted by Council by 31/05/2018 | n/a | Review and adoption of credible integrated development planning by Council by 31/05/2019 | credible integrated development planning was reviewed and by Council on the 31/05/2019 | Achieved | n/a | n/a | Office of the MM | OPEX | Council resolution and Integrated development plan
CCI03 |  | Improved Spatial Development Framework | 3 | Date of review and adoption of district Spatial Development framework by Council by 30/06/2019 | Date | n/a | Review and adoption of district Spatial Development framework by Council by 30/06/2019 | Review and adoption of district Spatial Development framework by Council by 30/06/2018 | n/a | Review and adoption of district Spatial Development framework by Council by 30/06/2019 | Spatial Development framework was reviewed and adopted by Council on the 31/05/2019 | Achieved | n/a | n/a | Social and Economic Services | OPEX | Council resolution and Spatial Development framework
CCI04 | To insure improved response to Disasters | Establishment of Disaster Management Structures & Systems | 4 | Date of review and adoption of Disaster Management Plan by Council by 30/06/2019 | Date | All | Review and adoption of Disaster Management Plan by Council by 30/06/2019 | Review and adoption of Disaster Management Plan by Council by 30/06/2018 | n/a | Date of review and adoption of Disaster Management Plan by Council by 30/06/2019 | Disaster Management Plan was reviewed and adopted by Council on the 30/06/2019 | Achieved | n/a | n/a | Social and Economic Services | OPEX | Council Resolution and Disaster Management Plan
CCI05 | To ensure sustainable protection and development of the environment | Development and implementation of environmental management Plan | 5 | Date of review and adotion of Environmental Management Plan provided by Council by 30/06/2019 | Date | All | Review and adotion of Environmental Management Plan provided by Council by 30/06/2019 | Review and adotion of Environmental Management Plan provided by Council by 30/06/2018 | n/a | Date of review and adotion of Environmental Management Plan provided by Council by 30/06/2019 | Environmental Management Plan provided was reviewed and adopted by Council on the 30/06/2019 | Achieved | n/a | n/a | Social and Economic Services | OPEX | Council Resolution and Environmental Management Plan