## Strategic RR 2021-2022
UTHUKELA DISTRICT MUNICIPALITY - STRATEGIC RISK REGISTER 2021/2022
[7 empty] | INHERENT RISK RATING (Prior to control measures put in place) |  |  |  |  | INHERENT RISK NAME | Existing Risk | CONTROL RATING | RESIDUAL RISK RATING (After control measures are put in place) |  | CONTROL NAME |  | RESIDUAL RISK NAME
| Risk Number | Risk Category | OBJECTIVE | RISK DESCRIPTION | CAUSES OF RISK | CONSEQUENCE | IMPACT (II) |  | L/HOOD (IL) |  | RATING (IR) |  | Mitigation / Current Controls |  | IMPACT (II) | Control Rating |  | RESIDUAL RISK RATING (IR) |  | Risk Mitigation Action Plan | Risk Owner | Action Owner | Date | Start Date | Due Date | Progress on Action Plan | Enterprise Risk Management Comments | Risk Management Comments | Internal Audit Comments
STRATEGIC RISK REGISTER 2021-2022
| SR/1 |  |  | Inability to design and implement systems of good governance within the municipality | 1)Non adherence to municipal policies. 2)Refusal to account for non-adherence to policies and standard operating procedures. 3)Poor planning on budget and IDP objectives. 4)Lack of training on policies. 5)Non-cascading of PMS to junior officials. 6)Non-timeous updating of the Compliance register. 7)Inconsistency in implementation of policies provision. | 1)Adverse audit outcomes. 2)Non-acheivement of municipal objectives. | 5 | 3.5 | 5 | 1.5 | 25 | CRITICAL | 1)Annual calendar of the meetings / dashboard. 2)Compliance register. 3)Governance committees. 4)Governance policies. 5)IDP 6)SDBIP | 80 |  |  | INADEQUATE | 20 | CRITICAL | 1)To develop standard operating procedures for all business processes. 2)Cascade PMS to all junior officials. 3)Re-establish the goverance committee with the terms of reference and training of the members of the committee. | MM | 1)All GM's 2)Manager PMS 3)MM |  | 1)01.07.2021 2)01.07.2021 3)01.07.2021 | 1)30.09.2021 2)31.12.2021 3)30.09.2021
| SR/2 |  |  | Inability to improve the systems of financial management across all sections of the municipality | 1)Low revenue collection caused by: 1.1)Non-review of debtors master files for consumer debtors. 1.2)Disputes caused by estimates. 2)Lack of tools of trade to conduct meter reading. 3)Failure to identify the root causes of the AG audit findings. 4)High water losses. 5)Non-workshopping of standard operating procedure manuals. 6)High expenditure rate caused by: 6.1)Interest charged 6.2)Non-cost reflective tariffs charged on consumers. 7)Non-implementation of internal audit findings. 8)Lack of accountability and enforcement of accountability by senior management. 9)Non-cascading of performance measurement systems to all levels of staff. | 1)Incurrence of UIF&W expenditure. 2)Adverse audit outcomes. 3)Tarnished image of the municipality. 4)Compromised service delivery. | 5 | 3.5 | 5 | 1.5 | 25 | CRITICAL | 1)AG and IA log 2)Interim Finance Committee (IFC) 3)Pre-authorization memo on unautorized expenditure by: 3.1)Finance 3.2)IFC 3.3)Municipal Manager 4)Revenue collections committee 5)Revenue enhancement strategy 6)Revision of limits for Eskom & Telkom to minimise interest charges. 7)SCM procurement plan | 80 |  |  | INADEQUATE | 20 | CRITICAL | 1)Manage the billing system to write-off very old and uncollectable consumer debts. 2)Convert from traditional meters to prepaid meter system. 3)Conduct a water loss audit / activity to assess; 3.1)Where the majority of water losses in incurred. 3.2)Amount of water consumed by the indigent population. 4)Workshop all standard operating procedure manuals to all levels of staff. 5)Request training from SCM municipal support Treasury for the: 5.1)Demand management unit (operating procedure) 5.2)Senior and middle management (procurement processes) 6)Review the consequence management tool to be aligned with the National consequence management circular. | MM | 1)CFO 2)CFO & GM:WS&TS 3)CFO & GM:WS&TS 4)CFO 5)CFO 6)All GM's |  | 1)01.07.2021 2)01.07.2021 3)01.07.2021 4)01.07.2021 5)01.07.2021 6)01.07.2021 | 1)30.09.2021 2)31.12.2021 3)30.09.2021 4)30.09.2021 5)30.09.2021 6)30.09.2021
| SR/3 |  |  | Inability to prevent biodiversity losses and loss of wetlands | 1)Alien plants and invasive species the reduce water availability. 2)Lack of dedicated official within the municipality to oversee the function. 3)Inadequate planning and implementation of environmental management. 4)Inadequate co-ordination between the municipaltiy and the sector department (EDTEA) and local municipalities. | 1)Droughts. 2)Loss of wetland | 5 | 3.5 | 5 | 1.5 | 25 | CRITICAL | 1)Catchment management forum. 2)Support from KZN Cogta (Mr Buthelezi) that removes invasive species. | 80 |  |  | INADEQUATE | 20 | CRITICAL | 1)Develop a consolidated plan on environmental management which will encompass: 1.1)Environmental management strategy. 1.2)Environmental management policy. 1.3)Annual implementation plan and conduct mapping to identify other alien plants. 1.4)Explore the possibility of revenue generation through selling of alien plants. | MM | 1)GM:SES |  | 1)01.07.2021 | 1)30.09.2021
| SR/4 |  |  | Delays in the provision of water and sanitation services equitably across the municipality | 1)Delays in the implementation of projects caused by the inadequate budget allocation in relation to the backlogs / business plans submitted. 2)Ageing existing infrastructure. 3)Lack of proactive maintenance of infrastructrue. 4)Vandalism of existing infrastracture. 5)illegal connections through the reticulation lines. | 1)Compromised service delivery 2)Community unrest | 4 | 2.8 | 5 | 1.5 | 20 | CRITICAL | 1)Infrastructure maintenance plan 2)Mayoral community awareness campaigns 3)Refurbishment and replacement of of existing infrastructure plan 4)Regional bulk infrastructure grant 5)Water and infrastructure grant | 80 |  |  | INADEQUATE | 16 | MAJOR | 1)Increasing the capacity of the existing water treatment works by yard connections with meters. 2)Conduct community awarness campaigns in the impact of illegal connections and vandalasim. 3)Develop business plan to source funding for the roll out of the infrastructure maintenance plan. 4)Develop standard operating procedure manual for water services unit. 5)Reprioritise from source to tap projects on the IDP and Budget. | MM | 1)GM:WS&TS 2)GM:WS&TS 3)GM:WS&TS 4)GM:WS&TS 5)GM:WS&TS, Chairperson of WS&TS portfolio & CFO |  | 1)01.07.2021 2)01.07.2021 3)01.07.2021 4)01.07.2021 5)01.07.2021 | 1)Ongoing 2)30.09.2021 3)30.09.2021 4)30.09.2021 5)30.09.2021
| SR/5 |  |  | Ineffective systems to prevent, detect and respond to fraud & corruption incidents | 1)Weak internal controls. 2)Non-rotataion of the members of bid committees. 3)Failure to rotate officials at high fraud area functions. | 1)Financial loss 2)Failure to meet the municipal objectives 3)Compromised service delivery 4)Community unrest | 5 | 3.5 | 4 | 1.2 | 20 | CRITICAL | 1)Annual fraud & corruption awarness campaigns 2)Fraud & corruption awarness day 3)Fraud prevention strategy 4)MPAC 5)Whistle-blowing hotline and email | 80 |  |  | INADEQUATE | 16 | MAJOR | 1)Develop a job rotation policy. 2)Consider the rotation duties of SCM officials. 3)Align the mandatory leave with the fraud prevention plan - identify the high fraud risk areas. 4)Rotate the SCM Bid committee members bi-annually. 5)Review the fraud prevention strategy & plan. 6)Conduct security checks for high fraud risk areas. | MM | 1)GM:CS 2)GM:CS & CFO 3)GM:CS 4)CFO 5)Risk Management Committee 6)GM:CS |  | 1)01.07.2021 2)01.07.2021 3)01.07.2021 4)01.07.2021 5)01.07.2021 6)01.07.2021 | 1)30.06.2022 2)30.09.2021 3)30.09.2021 4)30.09.2021 5)30.09.2021 6)30.09.2021
| SR/6 |  |  | Inability to provide adequate support to the Uthukela Development Agency | 1)Failure to provide adequate support in relation to - budget provision and resource allocation (human capacity). 2)Inability to recongnise the agency as a core function of the municipality. 3)Heavy reliance on the local municipalities for the sustainability of the agency. 4)Reclining economic situation of Uthukela. | 1)Failure to realise the municipality's vision and mission | 5 | 3.5 | 4 | 1.2 | 20 | CRITICAL | 1)LED strategy 2)Rural development strategy | 90 |  |  | UNSATISFACTORY | 18 | MAJOR | 1)Consider the secondment of the LED staff to the agency. 1.1)Relocation of all LED officials to the agency. 1.2)Transfer of the LED salary bill to the budget. 1.3)CEO's salary to be derived from the agency budget allocation. 2)Finalise and develop a memorandum of agreement with the agency which outlines: 2.1)Differentiation of duties. 2.2)Performance agreement with the district . | MM | 1)MM & GM:CS 2)GM:CS |  | 1)01.07.2021 2)01.07.2021 | 1)30.09.2021 2)30.09.2021
| SR/7 |  |  | Inability to recognise ICT as a strategic enabler | 1)Inadequate budget provision to support the implementation of ICT projects, and the replacement of ICT infrastructure. 2)Outdated server resulting in inability to process high volumes of data and frequent malfunctions. 3)Lack of tools of trade in relation to ICT for all municipal staff. 4)Failure to cash-back the depreciation of ICT assets. 5)Non-adherence of the ICT assets replacement policy of 3 years. 6)Non-procurement of relevant ICT assets. 7)Lack of knowledge resulting in limited interests in ICT programmes and non-prioritization of ICT. 8)Failure to use ICT systems that are aleady in place. 9)Poor composition of the ICT steering committee. | 1)Failure to exploit the benefits of 4IR. 2)Compromised service delivery | 5 | 3.5 | 4 | 1.2 | 20 | CRITICAL | 1)Business continuity plan 2)Change management policy 3)Firewall with accompanying policy. 4)ICT 5 year strategic plan 5)ICT framework policy 6)ICT project management policy 7)ICT security policy 8)ICT steering committee 9)Incident management policy 10)MANCO reports 11)User management policy 12)Uthukela E-portal | 90 |  |  | UNSATISFACTORY | 18 | MAJOR | 1)Conduct awareness campaigns & training on the e-portal to the communities. 2)Conduct staff awareness campaigns on the benefits of e-business. 2.1)Live streaming of events. 2.2)Uploads on the municipal website 3)Review the compostion of the ICT steering committee to include: CFO & Senior managers. 4)Consider the cash-backing of depreciation of ICT assets. 5)Finalise plans with Munsoft on the procurment & maintenance of the server. | MM | 1)ICT Manager 2)ICT Manager 3)GM:CS & MM 4)ICT Manager 5)ICT Manager |  | 1)01.07.2021 2)01.07.2021 3)01.07.2021 4)01.07.2021 5)01.07.2021 | 1)30.09.2021 2)30.09.2021 3)30.09.2021 4)30.06.2022 5)30.09.2021
| SR/8 |  |  | Ineffective communication with internal and external stakeholders leading to service delivery protests | 1)Failure to meet on a timely basis of public participation structures. 2)Non-timeous reports to the public participation office by water service unit. | 1)Community unrest 2)Vandalism of existing infrastructure 3)Financial loss | 4 | 2.8 | 4 | 1.2 | 16 | MAJOR | 1)District public particpation forum 2)Operation sukuma sakhe 3)Quarterly reports to CoGta on the effectiveness of public participation 4)Rapid response structures 5)Speakers forum 6)Stakeholders forum: Amakhosi & Local municipalities 7)Ward committees 8)Weekly meetings with water services unit | 65 |  |  | MODERATE | 10.4 | MODERATE | 1)Develop a programme to: 1.1)Encourage communities to make timely payments. 1.2)Dangers and threats related to illegal connections. 1.3)Address the issues on vandalism 2)Develop a programme to educate communities on how local government operates. 2.1)Attending of budget preparation meetings. 2.2)SCM processes 2.3)Duties of LM's and the District | MM | 1)Public Participation Manager 2)Public Participation Manager & CFO |  | 1)01.07.2021 2)01.07.2021 | 1)30.09.2021 2)30.09.2021
Strategic Risk Tolerance Table
| Critical |  |  | Unacceptable | Risks cannot be tolerated at their current levels, activities that bring risks must be ceased until appropriate controls to reduce risks are developed and implemented. | 3
| Major |  |  | Tolerable | Level of risks must be reduced unless costs associated with controls exceed associated benefits. | 4
| Moderate |  |  | Tolerable | Risks at this level will only be reduced when benefits exceed the cost of reduction. | 1
| Minor |  |  | Tolerable | Risks at this level will only be reduced when benefits exceed the cost of reduction. | 0
| Insignificant |  |  | Acceptable | Risks are accepted at their current levels. | 0
8
Note on P8: HELP ON RATINGS: Use the guidelines tabulated in the attached Risk Matrix sheet to guide you along with the ratings. Make sure that you do these ratings after Control Measures are considered and/or put in place.