## Sheet1
2023/2024 DRAFT SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN
OBJECTIVE | STRATEGY | KPI No. | KEY PERFORMANCE INDICATOR | MEASURABLE UNIT | ANNUAL TARGET | QUARTERLY TARGETS | [8 empty] | PORTFOLIO OF EVIDENCE
[6 empty] | Q1 | Q2 | Q3 | Q4 | Q2 Actual | Achieved/Not Achieved | Reason for Variance | Corrective Measure | RESPONSIBLE PERSON
GOOD GOVERNANCE
To ensure compliance with legislation applicable to municipal entities and principals outlined in the King III Report | Adherence to the MFMA, MSA, and the Company's Act | UEDA 01 | Compliance Checklist reviewed by Audit Committee and adopted by Board 30 June 2024 | Date reviewed by Audit Committee. Date adopted by Board. | 1 Compliance checklists reviewed by Audit Committee and adopted by the Board by 30 June 2024 | n/a | n/a | n/a | 1 Compliance checklists reviewed by Audit Committee and adopted by the Board by 30 June 2024 | n/a | n/a | n/a | n/a | Ms S Maphalala- Corporate Service Officer | Compliance Checklist,Resolution Board
| Relationship with Parent Municipality (UTDM). | UEDA02 | Performance reports submitted to UTDM | Number of reports submitted to the accounting officer | 4 Quarterly Performance reports submitted to UTDM by 30 June 2024 | 1 Quarterly Performance report submitted to UTDM by 30 September 2023 | 1 Quarterly Performance report submitted to UTDM by 31 December 2023, MID-Year report to be submitted | 1 Quarterly Performance report submitted to UTDM by 31 March 2024 | 1 Quarterly Performance report submitted to UTDM by 30 June 2024 | 1 Quarterly Performance report submitted to UTDM by 31 December 2023 | Achieved | n/a | n/a | Ms S Maphalala- Corporate Service Officer | Quarterly reports,Proof of Submission
| Oversight on performance; risk and financial controls | UEDA03 | Quarterly Board meetings | Number of meetings | 4 Board meetings by 30 June 2024 | 1 Board meeting by 30 September 2023 | 1 Board meeting by 31 December 2023 | 1 Board meeting by 31 March 2024 | 1 Board meeting by 30 June 2024 | 1 Board meeting conveved on the 10 November 2023 | Achieved | n/a | n/a | Ms S Maphalala-Corporate Service Officer | Notice ,Agenda , Signed minutes and attendance registers
| Ensure good governance; performance management; risk assessment and financial controls. | UEDA04 | Quarterly internal Audit Committee Reports by 30 june 2024 | Number of reports | 4 internal Audit Committee Reports by 30 June 2024 | 1 internal Audit Committee report by 31 September 2023 | 1 internalAudit Committee report by 31 December 2023 | 1 internal Audit Committee report by 31 March 2024 | 1 internalAudit Committee report 30 June 2024 | 1 internalAudit Committee report by 31 December 2023 | Achieved | n/a | n/a | Ms S Maphalala- Corporate Service Officer | Internal Audit reports
ORGANISATIONAL DEVELOPMENT AND TRANSFORMATION
Implement Performance Management | To improve delivery through the implementation of a performance management system | UEDA05 | Conduct employee Performance Management reviews by 30 June 2024 | Number of employees | 4 employee entered into an employee performance reviews by 30 June 2024 | n/a | 4 employee entered into an employee performance reviews by 31 December 2023 | n/a | 4 employee entered into an employee performance reviews by 30 June 2024 | 4 employee entered into an employee performance reviews by 31 December 2023 | Achieved | n/a | n/a | Ms S Maphalala- Corporate Service Officer | Signed reports
To improve the capacity of staff for service delivery |  | UEDA06 | Implemenation of skills training programmes by 30 June 2024 | Number of Training Session | Two(2) training session held for employees by 30 June 2024 | n/a | n/a | 1 training session held for employees by 31 March 2024 | 1 training session held for employees by 30 June 2024 | n/a | n/a | n/a | n/a | Ms S Maphalala- Corporate Service Officer | Signed reports
|  | UEDA07 | Adoption human resources and related policies by 30 June 2024 | Number of policies adopted | 14 Human resources and related policies adopted by the Board by 30 June 2024 | n/a | n/a | review policies by 31 March 2024 | 14 Human resources and related policies adopted by the Board by 30 June 2024 | n/a | n/a | n/a | n/a | Ms S Maphalala- Corporate Service Officer | Proof of adoption
FINANCIAL VIABILITY AND MANAGEMENT
| To ensure effective reporting and compliance | UEDA08 | Submission of credible annual fiancial statements to the Auditor-General by 31 August 2023 | Date of submission of the report | Submission of annual financial statements to the Auditor-General by 31 August 2023 | Submission of annual financial statements to the Auditor-General by 31 August 2023 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Ms Fanele Mbuyisa - Finance&Investment Officer | Proof of submission
|  | UEDA09 | Submission of credible annual performance report to the Auditor-General by 30 August 2023 | Date of submission of the report | Submission of annual performance report to the Auditor-General by 31August 2023 | Submission of annual performance report to the Auditor-General by 31 2023 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Ms Fanele Mbuyisa - Finance & Investment Officer | Proof of submission
|  | UEDA 10 | Submission of mid-term budget and performance assessment report to Board and UTDM by 20 January 2024 | Date of submission of the report | Submission of mid-term budget and performance assessment report to Board and UTDM by 20 January 2024 | n/a | n/a | Submission of mid-term budget and performance assessment report to Board and UTDM by 20 January 2024 | n/a | n/a | n/a | n/a | n/a | Ms Fanele Mbuyisa - Finance & Incestment Officer | Proof of submission
|  | UEDA11 | Submission of monthly financial reports to the board and UTDM by 30 June 2024 | Date of submission of the report | 12 Submission of monthly financial reports reportett to Board and UTDM by 30 June 2024 | 3 monthly financial reports by 31 September 2023 | 3 monthly financial reports by 31 December 2023 | 3 monthly financial reports by 31 March 2024 | 3 monthly financial reports by 30 June 2024 | 3 monthly financial reports by 31 December 2023 | Achieved | n/a | n/a | Ms Fanele Mbuyisa -Finance and Investment Officer | Proof of submission
|  | UEDA 12 | Submission of annual budget in terms of S87 of MFMA to the parent municipality by 31 January 2024 | Date of submission of the report | Submission of annual budget in terms of S8 of MFMA | n/a | n/a | Annual budget | n/a | n/a | n/a | n/a | n/a | Ms Fanele Mbuyisa- Finance & Investment Officer | Proof of submission
|  | UEDA 13 | Submission of Annual Budget in terms of S87 of the MFMA to the parent municipality, 30 days before the start of the financial year | Date of submission of the report | submission of annual budget in terms of S7 of MFMA | n/a | n/a | n/a | Annual budget | n/a | n/a | n/a | n/a | Ms Fanele Mbuyisa- Finance & Investment Officer | board resolution
LOCAL ECONOMIC DEVELOPMENT
OBJECTIVE | STRATEGY |  | KEY PERFORMANCE INDICATOR | MEASURABLE UNIT | ANNUAL TARGET | QUARTERLY TARGETS | [8 empty] | PORTFOLIO OF EVIDENCE
[6 empty] | Q1 | Q2 | Q3 | Q4 | Q2 Actual | Achieved/Not Achieved | Reason for Variance | Corrective Measure
To bring infracture & facilities that will help large and SMMEs to thrive at uThukela District | To create an enabling and conducive environment for both local and international businesses to thrive | UEDA 14 | Number of engangements to develop bulk infrastructure for economic opportunities | Number of meetings | Three (3)engangements held with relevant stakeholders in relation to development of bulk infrastructure for economic opportunities | One engagement to facilitate access to land for development by 30 September 2023 | One (1) engangement to facilitate the establishment of Colenso Power Project by 31 December 2023 | One engagement to facilitate a study to provide free wifi in uThukela District by 31 March 2024 | n/a | One (1) engangement to facilitate the establishment of Colenso Power Project held on the 08 December 2023 | Achieved | n/a | n/a | Ms Fanele Mbuyisa- Finance & investment Officer | Notice,Agenda,Attendance Register,Minutes
|  | UEDA 15 | Number of PSC engagements in relation to the establishment of DUT setellite office by 30 June 2023 | Number of meetings | 4 engagements held in relation to the establishment of DUT satellite Campus in Ladysmith by 30 June 2024 | One(1) engagement held in relation to establishment of DUT Satellite Campus by 30 September 2023 | One(1) engagement held in relation to the establishment of DUT setellite office by 31 December 2023 | One (1) engagement held in relation to the establishment of DUT setellite office 31 March 2024 | One (1) PSC engagement held in relation to the establishment of DUT setellite office by 30 June 2024 | Zere(0) engagement held in relation to the establishment of DUT setellite office by 31 December 2023 | Not Achieved |  |  | Ms Fanele Mbuyisa- Finance & investment Officer | Notice,Agenda,Attendance Register,Minutes
|  | UEDA 16 | Number of meetings held in the establishment of Clothing and Textile Special Economic Zone by 30 June 2023 | Number of meetings | Two (2) engagements held on the establishment of Special Economic Zone by 30 June 2024 |  | One (1) meetings held on the establishment of Special Economic Zone by 31 December 2023 |  | One (1) meetings held on the establishment of Special Economic Zone by 30 June 2024 | One (1) meetings held on the establishment of Special Economic Zone by 31 December 2023 | Achieved | n/a | n/a | Ms Fanele Mbuyisa- Finance & investment Officer | Notice,Agenda,Attendance Register,Minutes
|  | UEDA 17 | Number of engagementsheld to support informal economy and small enterprises | Number of meetings | Four(4) engagements to support informal economy and small enterprises by 30 June 2024 | One (1)engagement to support informal economy and small enterprises by 30 September 2023 | One (1)engagement to support informal economy and small enterprises by December 2023 | One (1)engagement to support informal economy and small enterprises by 31 March 2023 | One (1)engagement to support informal economy and small enterprises by 30 June 2024 | Zero (0)engagement to support informal economy and small enterprises by December 2023 | Not Achieved |  |  | Ms Fanele Mbuyisa- Finance & investment Officer | Notice,Agenda,Attendance Register,Minutes
|  | UEDA 18 | Number of engagements held to expand the manufacturing | Number of meetings | Four(4) engagements held to expand the manufacuring sector by 30 June 2024 | One (1 ) engagements heldwith relevant stakeholders to review the district investment promotion and facilitation strategy by 30 September 202 | One (1) engagement to develop a database of all zoned industrial, vacant and underutilised spaces by 31 December 2023 | One (1) engagements heldwith relevant stakeholders to facilitate phase 2 of CMT(Pro Textile) by 31 March 2024 | Four (4) engagements held with relevant stakeholders to secure an investor for Watersmeet Spring Water Bottled Project by 30 June 2024 | Zero (0) engagement to develop a database of all zoned industrial, vacant and underutilised spaces by 31 December 2023 | Not Achieved |  |  | Ms Fanele Mbuyisa- Finance & investment Officer | Notice,Agenda,Attendance Register,Minutes
|  | UEDA 19 | Number of engagements to develop strategic transport infrastructure | Number of meetings | Four(4) engagements to develop strategic transport infrastructure by 30 June 2024 | One(1) engagement held with relevant stakeholders to fast track Alfred Duma Aerodrome Project by 30 September 2023 | One(1) engagement held with relevant stakeholders concerning SIP2: Corridor plan to improve the logistic capability of the N3 by 31 December 2023 | One(1) engagement held with relevant stakeholders concerning the implementation of N11 Corridor Plan by 31 March 2024 | One (1) engagement held in facilitation of Escourt Intermodal Terminal or Isitimela Rapid Cargo Project by 30 June 2024 | Zero(0) engagement held with relevant stakeholders concerning SIP2: Corridor plan to improve the logistic capability of the N3 by 31 December 2023 | Not Achieved |  |  | Ms Fanele Mbuyisa- Finance & investment Officer | Notice,Agenda,Attendance Register,Minutes
To position UTD as a first choice world class tourism destination | To mobilise and promote the use of local resources and skills thus ensuring maximising local economic development (tourism) | UEDA 20 | Number of in-house tourism training & development workshops conducted with the tourism interns & officers | Number of trainings | Four (4) in-house tourism training & development workshops conducted with the tourism interns & officers by 30 June 2024 | One (1) in-house tourism training & development workshops conducted with the tourism interns & officers by 30 September 2023 | One (1) in-house tourism training & development workshops conducted with the tourism interns & officers by 31 December 2023 | One (1) in-house tourism training & development workshops conducted with the tourism interns & officers by 31 March 2024 | One (1) in-house tourism training & development workshops conducted with the tourism interns & officers by 30 June 2024 | One (1) in-house tourism training & development workshops conducted with the tourism interns & officers by 01 November 2023 | Achieved | n/a | n/a | Ms N Sithole - Programmes Officer (Agriculture (RASET)& Tourism) | Signed Reports Attendence registers & pictures of training sessions and traning contents
|  | UEDA 21 | Number of District Tourism Marketing updates by 30 June 2023 | Number of tourism marketing updates | Four(4) District Tourism Marketing updates by 30 June 2024 | One (1) District Tourism Marketing update by 30 September 2023 | One (1) District Tourism Marketing update by 31 December 2023 | One (1) District Tourism Marketing update by 31 March 2024 | One (1) District Tourism Marketing update by 30 June 2024 | One (1) District Tourism Marketing update by 31 December 2023 | Achieved | n/a | n/a | Ms N Sithole - Programmes Officer (Agriculture (RASET)& Tourism) | Signed Reports, Municipal Websites, Social media platforms
|  | UEDA 21.1 | Lobbying for the provincial tourism authority and municipalities to ensure that tourism SMMEs are listed and promoted on their websites | Lobbying for the listing of the tourism SMME's | Four (4) Lobbying for the provinvial tourism authority and municipalities to ensure that tourism SMME's are listed and promoted on their websites | One (1) email lobbying for the listing of the tourism SMME's by 30 September 2023 | One (1) email lobbying for the listing of the tourism SMME's by 31 December 2023 | one (1) email lobbying for the listing of the tourism SMME's by 31 March 2024 | one (1) email lobbying for the listing of the tourism SMME's by 30 June 2024 | One (1) email lobbying for the listing of the tourism SMME's by 31 December 2023 | Achieved | n/a | n/a | Ms N Sithole - Programmes Officer (Agriculture (RASET)& Tourism) | Email print outs
|  | UEDA 22 | Number of Tourism Stakeholder Analysis by 30 June 2023 | Number of tourism stakeholder analysis | One (1) Tourism Stakeholder Analysis by 30 June 2023 | One (1) Tourism Stakeholder Analysis noted by Board by 30 June 2024 | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Ms N Sithole - Programmes Officer (Agriculture (RASET)& Tourism) | Stakeholder analysis Document
|  | UEDA 22.1 | Number of Tourism stakeholder Engagement Plan by 30 June 2024 | Number of Tourism Stakeholder Engagement Plan | One (1) Tourism Stakeholder Engagement Plan by 30 June 2024 | One (1) Tourism Stakeholder Engagement Plan by 30 September | n/a | n/a | n/a | n/a | n/a | n/a | n/a | Ms N Sithole - Programmes Officer (Agriculture (RASET)& Tourism) | Stakeholder engagement plan document
|  | UEDA 22.2 | Number of stakeholders engagement held by 30 June 2024 | Number of stakeholders engagement | Four (4) Number of stakeholders engagements held by 30 June 2023 | One (1) stakeholders engagement held with Trade by 30 September 2023 | One (1) stakeholders engagement held with Trade by 31 December 2023 | One(1) stakeholders engagement held with Trade by 31 March 2024 | One(1) stakeholders engagement held with Trade by 30 June 2024 | One (1) stakeholders engagement held with Trade by 31 December 2023 | Achieved | n/a | n/a | Ms N Sithole - Programmes Officer (Agriculture (RASET)& Tourism) | Attendance registers, Reports, Pictures
|  | UEDA 23 | Number of tourism activation programs conducted by 30 June 2024 | Number of tourism activation programs | Four (4) tourism activation programs conducted by 30 June 2024 | One (1) tourism activation programs conducted by 30 September 2023 | One (1) tourism activation programs conducted by 31 December 2023 | One (1) tourism activation programs conducted by 31 March 2024 | One (1) tourism activation programs conducted by 30 June 2024 | Zero (0) tourism activation programs conducted by 31 December 2023 | Not Achieved | There was inadequate marketing material from the product owner |  | Ms N Sithole - Programmes Officer (Agriculture (RASET)& Tourism) | Reports , Event Pictures
|  | UEDA 24 | Lobbying for funding for the construction of Phase one of uMhlumayo Cultural Village Project by 30 June 2024 | Lobbying for funding | Four (4) Lobbying for funding for the construction of Phase one of uMhlumayo Cultural Village Project by 30 June 2024 | One (1) Lobby (Proposal submission) for uMhlumayo Cultural Village Project by 30 September 2023 | One (1) Lobby (Proposal submission) for uMhlumayo Cultural Village Project by 31 December 2023 | One (1) Lobby (Proposal submission) for uMhlumayo Cultural Village Project by 31 March 2024 | One (1) Lobby (Proposal submission) for uMhlumayo Cultural Village Project by 30 June 2024 | Zero (0) Lobby (Proposal submission) for uMhlumayo Cultural Village Project by 31 December 2023 | Not Achieved | There were no funds for this initiative |  | Ms N Sithole - Programmes Officer (Agriculture (RASET)& Tourism) | Submitted Proposals
|  | UEDA 25 | Coordinate accreditation of UEDA with the Tourism specific SETA by 30 June 2024 | Coordinate accreditation | One (1) Coordinate accreditation of UEDA with the Tourism specific SETA by 30 June 2024 | one (1) meeting with SETA to facilitate the accreditation of UEDA with the Tourism specific SETA by 30 September 2023 | One (1) Follow up meeting with SETA to facilitate the accreditation of UEDA with the Tourism specific SETA by 31 December 2023 | One (1) Follow up meeting with SETA to facilitate the accreditation of UEDA with the Tourism specific SETA by 31 March 2024 | one (1) report on the coordination of the accreditation of UEDA with the Tourism specific SETA by 30 June 2024 | Zero (0) Follow up meeting with SETA to facilitate the accreditation of UEDA with the Tourism specific SETA by 31 December 2023 | Not Achieved |  |  | Ms N Sithole - Programmes Officer (Agriculture (RASET)& Tourism) | Meeting minutes, attendance registers & report
|  | UEDA 26 | Conduct Familiarisation trips on all tourism routes | Conduct Familiarisation trips | Eight (8) Familiarisation trips conducted by 30 June 2024 | Two (2) Familiarisation trips conducted by 30 September 2023 | Two (2) Familiarisation trips conducted by 31 December 2023 | Two (2) Familiarisation trips conducted by 31 March 2024 | Two (2) Familiarisation trips conducted by 30 June 2024 | Two (2) Familiarisation trips conducted by 31 December 2023 | Achieved | n/a | n/a | Ms N Sithole - Programmes Officer (Agriculture (RASET)& Tourism) | Reports, Pictures
|  | UEDA 27 | reports submitted farmer identification (1), feed procurement and distribution (1), chicken production (2) by 30 June 2024 | Reports | Four(4) reports submitted farmer identification (1), feed procurement and distribution (1), chicken production (2) by 30 June 2024 | Identification of 10 chicken farmers around the district that can procuce 250 (min) broilers a week by 30 September 2023 | Feed procurement and distribution, 25(40kg) feed bags per farmer by 31 December 2023 | Chicken production, minimum 500 per farmer per month. Assistance with transport by 31 March 2024 | Chicken production, minimum 500 per farmer per month. Assistance with transport by 30 June 2024 | Feed procurement and distribution, 25(40kg) feed bags per farmer by 31 December 2023 | Not Achieved |  |  | Ms N Sithole - Programmes Officer (Agriculture (RASET)& Tourism) | reports
To develop sustainable commercialisation of Agriculture and Agribusiness industries and the implementation of RASET in the uThukela District | To mobilise and promote the use of local resources and skills thus ensuring maximising local economic development (Agriculture) | UEDA 28 | reports submitted farmer identification, seed procurement and distribution (1), monitoring visits, potato harvests (1), Project evaluation (1) by 30 June 2024 | Reports | Four(4) reports submitted farmer identification, seed procurement and distribution (1), monitoring visits, potato harvests (1), Project evaluation (1) by 30 June 2024 | Identification of 10 potatoe farmers around the district to plant 2 hectares of land each and be assisted with 10 bags of potato seeds each by 30 September 2023 | Monitoring, harvest (2 tons per farmer) potatoes per farmer. Assistance with transport by 31 December 2023 | Finishing harvest of remaining potatoes to reach previous quarter's targets by 31 March 2024 | Project evaluation and adjusments by 30 June 2024 |  | Not Achieved |  |  | Ms N Sithole - Programmes Officer (Agriculture (RASET)& Tourism) | Reports
|  | UEDA 29 | Four(4) reports submitted farmer identification (1), bean seed procurement and distribution (1), monitoring visits, bean harvests (1), Project evaluation (1) by 30 June 2024 | Reports | Four(4) reports submitted farmer identification (1), bean seed procurement and distribution (1), monitoring visits, bean harvests (1), Project evaluation (1) by 30 June 2024 | Identification of 10 bean farmers around the district that can produce 5ton beans by 30 September 2023 | Seed procurement and distribution, 10 (25kg) seed bags per farmer by 31 December 2023 | Bean harvests, min 2 tons per farmer, assistance with transport 31 March 2024 | Project evaluation and adjustments by 30 June 2024 |  | Not Achieved |  |  | Ms N Sithole - Programmes Officer (Agriculture (RASET)& Tourism) | Reports
|  | UEDA 30 | Four(4) reports submitted farmer identification (1), soya seed procurement and distribution (1), monitoring visits, soya harvests (1), Project evaluation (1) by 30 June 2024 | Reports | Four(4) reports submitted farmer identification (1), soya seed procurement and distribution (1), monitoring visits, soya harvests (1), Project evaluation (1) by 30 June 2024 | Identification of 10 soya bean farmers that can produce 5 ton soya by 30 September 2023 | Seed procurement and distribution, 10 (25kg) seed bags per farmer by 31 December 2023 | Soya production, min 2 tons per farmer, assistance with transport by 31 March 2024 | Project evaluation and adjustments by 30 June 2024 |  | Not Achieved |  |  | Ms N Sithole - Programmes Officer (Agriculture (RASET)& Tourism) | reports
|  | UEDA 31 | Four (4) reports submitted on groundnut seed procurement and distribution (1), Monitoring (1), Harvesting, Evaluation (1) by 30 June 2024 | Reports | Four (4) reports submitted on groundnut seed procurement and distribution (1), Monitoring (1), Harvesting, Evaluation (1) by 30 June 2024 | Procurement and distribution of 150 (40kg) bags of peanut seeds to farmers of Nkaseni, Ngodini and Sahlumbe by 30 September 2023 | Monitoring of peanut cultivation, 2 visits per farmer by 31 December 2023 | Groundnut production, min 50 tons to be harvested. Assistance with transport by 31 March 2024 | Project evaluation and adjustments by 30 June 2024 |  | Not Achieved |  |  | Ms N Sithole - Programmes Officer (Agriculture (RASET)& Tourism) | Reports
|  | UEDA 32 | Reports submitted on farmer identification (1), butternut seed procurement and distribution (1), Harvesting (1), Evaluation (1) by 30 June 2024 | Reports | Four (4) reports submitted on farmer identification (1), butternut seed procurement and distribution (1), Harvesting (1), Evaluation (1) by 30 June 2024 | Identification of 10 butternut farmers that can grow min 2 hectares of land by 30 September 2023 | seed procurement and distribution, 10 (1kg) seed pockets per farmer by 31 December 2023 | Butternut production, min 2 tons per farmer, assistance with transport by 31 March 2024 | Project evaluation and adjustments by 30 June 2024 |  | Not Achieved |  |  | Ms N Sithole - Programmes Officer (Agriculture (RASET)& Tourism) | report
|  | UEDA 33 | Reports on enquiries and engagements(1) Identification of farmers, maize seeds procurement and distribution (1), Monitoring (1), Harvest, evaluation (1) by 30 June 2024 | Reports | Four(4) reports on enquiries and engagements(1) Identification of farmers, maize seeds procurement and distribution (1), Monitoring (1), Harvest, evaluation (1) by 30 June 2024 | Investigate (3) and engage with (2) markets availble for maize farmer by 30 September 2023 | Mobilise 5 farmers to join maize production (2 Hectares). Procure and distribute 10 (40kg) seed bags per farmer by 31 December 2023 | Monitoring of all 5 farmers, 2 visits per farmer by 31 March 2024 | Harvest 2 tons per farmer. Assist with transport. Project evaluation and adjustments by 30 June 2024 |  | Not Achieved |  |  | Ms N Sithole - Programmes Officer (Agriculture (RASET)& Tourism) | emails and attendance register and report
|  | UEDA 34 | Four reports submitted on livestock markets held by 30 June 2024 | Reports | Four(4) Quarterly reports submitted on livestock markets. | One(1) report submitted t on livestock market held by 30 September 2023 | One(1) report submitted on livestock market held by 31 Dec 2023 | One(1) report submitted on livestock market held by 31 March 2024 | One(1) report submitted on livestock market held by 30 June 2024 | One(1) report submitted on livestock market held by 31 Dec 2023 | Achieved | n/a | n/a | Ms N Sithole - Programmes Officer (Agriculture (RASET)& Tourism) | report
|  | UEDA 35 | reports submitted on Cannabis/hemp production | Reports | Four (4) reports on engagements with stakeholders. Separate meetings with each stakeholder and 3 PSC meetings by 30 June 2023 | One (1) report on 1 engagement with DARD, 1 with ILM, ADLM and UTDM (separately) on a funding model, 1 with all stakeholders. Formation of PSC. By 30 September 2023 | One (1) report on identification and mapping of aMaKhosi land set aside for cannabis farming. 1 PSC meeting by 31 December 2023 | Two (2) engagement with Druids. 1 PSC meeting by the 31 March 2024 | Compilation of 1 application per each iNkosi (3 aMaKhosi in ADLM and 2 in ILM). PSC meeting by 30 June 2024 | Zero(0) report on identification and mapping of aMaKhosi land set aside for cannabis farming. 1 PSC meeting by 31 December 2023 | Not Achieved |  |  | Ms N Sithole - Programmes Officer (Agriculture (RASET)& Tourism) | Reports, Notice, Agenda, Minutes, Attendance register
|  | UEDA 36 | reports submitted on business plan, fixing of machinery, funding application (1), tilling for 3rd parties, follow up (1) by 30 June 2024 | Reports | Four reports submitted on business plan, fixing of machinery, funding application (1), tilling for 3rd parties, follow up (1) by 30 June 2024 | Writing of business plan. Fixing of three tractors. Funding applications to 3 funders by 30 September 2023 | Use of machinery to cultivate (10ha) land for other farmers at a fee to get funds to restart chicory farming. Follow up on funding applications by 31 December 2023 | Procure chicory seeds (100 kg ) by 31 March 2024 | Comence with chicorry production (100 hetres) by 30 June 2024 |  | Not Achieved |  |  | Ms N Sithole - Programmes Officer (Agriculture (RASET)& Tourism) | Reports, business plan and Aknowledgement of receipt