## MID YEAR
SERVICE DELIVERY AND BUDGET IMPLEMENTATION PLAN (SDBIP): 2023/2024 MID YEAR
NAME OF MUNICIPALITY: UTHUKELA DISTRICT MUNICIPALITY | [20 empty] | FINANCIAL YEAR ENDED: 30 JUNE 2024
IDP / SDBIP NO. | Objective | Strategy | Indicator No. | Key Performance Indicator | KPI Measurement | Ward No. | Baseline:2022/2023 |  | 2023/2024 Projections | [6 empty] | CONSOLIDATED 2022/2023 MID - YEAR |  |  |  |  | Responsible Department | Budget | Portfolio of Evidence
[7 empty] | Annual Target | Annual Actual | Annual Target | Quarter 1 | Quarter 1 Actual | Quarter 2 | Q3 | Q4 | Quarter 2 Actual | Q1&Q2 Target | Q1&Q2 Actual | Achieved/Not Achieved | Reason for Variance | Corrective Measure
KPA 1: MUNICIPAL TRANFORMATION AND INSTITUTIONAL DEVELOPMENT
MTID01 | To ensure a functional Performance Management System | Implementation of PMS Policy & Framework | 1 | Date of adoption Performance Management System by Council by 30/06/2024 | Date of adoption | n/a | Adoption of Performance Management System by Council by 30/05/2023 | Adoption of Performance Management System by Council by 30/05/2023 | Adoption of Performance Management System by Council by 30/06/2024 | N/A | N/A | N/A | N/A | Adoption of Performance Management System by Council by 30/06/2024 | N/A | N/A | N/A | N/A | N/A | N/A | Office of the MM | OPEX | Council resolution, PMS Policy,Framework and Standard Operating Procedures
MTID02 |  |  | 2 | Number of quarterly performance reports submitted by departments to the Office of the Municipal Manager by 30/06/2024 | Number of reports | n/a | 4 quarterly performance reports submitted by departments to the Office of the Municipal Manager by 30/06/2023 | 4 quarterly performance reports submitted by departments to the Office of the Municipal Manager by 30/06/2023 | 4 quarterly performance reports submitted by departments to the Office of the Municipal Manager by 30/06/2024 | 1 quarterly performance report submitted by departments to the Office of the Municipal Manager by 30/09/2023 | 1 quarterly performance report submitted by departments to the Office of the Municipal Manager by 30/09/2023 | 1 quarterly performance report submitted by departments to the Office of the Municipal Manager by 31/12/2023 | 1 quarterly performance report submitted by departments to the Office of the Municipal Manager by 31/03/2024 | 1 quarterly performance report submitted by departments to the Office of the Municipal Manager by 30/06/2024 | 2 quarterly performance report submitted by departments to the Office of the Municipal Manager by 31/12/2023 | Two (2) quarterly performance report submitted by departments to the Office of the Municipal Manager by 31/12/2023 | Two (2) quarterly performance report submitted by departments to the Office of the Municipal Manager by 31/12/2023 | Achieved | N/A | N/A | All Departments | OPEX | Signed copies of reports & Aknowledgement letters
MTID03 |  |  | 3 | Date of submission of Mid-Year Performance Report to the Mayor and Treasuries by 25/01/2024 | Date of submission | n/a | Submission of Mid-Year Performance Report to the Mayor and Treasuries by 25/01/2023 | Mid-Year Performance Report to the Mayor and Treasuries on the 24/01/2023 | Date of submission of Mid-Year Performance Report to the Mayor and Treasuries by 25/01/2024 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Office of the MM | OPEX | Proof of submission and Mid-Year Performance Report
MTID04 |  |  | 4 | Date of submission of unaudited Annual Performance Report to the Auditor-General by 31/08/2023 | Date of submission | n/a | Submission of unaudited Annual Performance Report to the Auditor-General by 31/08/2022 | Unaudited Annual Performance Report submitted to the Auditor-General on the 31/10/2022 | Submission of unaudited Annual Performance Report to the Auditor-General by 31/08/2023 | Submission of unaudited Annual Performance Report to the Auditor-Genral by 31/08/2023 | The unaudited Annual Performance Report was submitted to the Auditor-General on the 31/08/2023 | N/A | N/A | N/A | N/A | Submission of unaudited Annual Performance Report to the Auditor-Genral by 31/08/2023 | The unaudited Annual Performance Report was submitted to the Auditor-General on the 31/08/2023 | Achieved | N/A | N/A | Office of the MM | OPEX | Proof of submission and copy of the Annual Performance Report
MTID05 |  |  | 5 | Date of tabling of Annual Report to Council by 31/03/2024 | Date of tabling | n/a | Adoption of Annual Report by Council by 31/03/2023 | Annual Report adopted by Council on 30/04/2023 | Tabling of Annual Report to Council by 31/03/2024 | N/A | N/A | Tabling of Annual Report to Council by 31/03/2024 | Tabling of Annual Report to Council by 31/03/2024 | N/A | Tabling of Annual Report to Council by 31/03/2024 | N/A | N/A | N/A | N/A | N/A | Office of the MM | OPEX | Council resolution
MTID06 |  |  | 6 | Number of formal section 54/56 managers performance reviews conducted by Performance Review Panels by 30/06/2024 | Number of formal reviews | n/a | Two (2) formal section 54/56 managers' performance reviews conducted by 30/06/2023 | Two (2) formal section 45/56 managers' performance reviews conducted by 30/06/2023 | Two (2) formal section 54/56 managers' performance reviews conducted by Performance Review Panels by 30/06/2024 | N/A | N/A | N/A | N/A | Two (2) formal section 54/56 managers' performance reviews conducted by Performance review Panels by 30/06/2024 | N/A | N/A | N/A | N/A | N/A | N/A | Office of the MM | OPEX | Signed Assessment Reports
MTID07 | To ensure fucntional risk and compliance management | Review and adopt risk and compliance governance policies | 7 | Number of risk and Compliance governance Policies adopted by Council by 30/06/2024 | Date of review | n/a | Review and adoption of risk management framework by Council by 30/06/2023 | Risk management framework reviewed and adopted by Council on the 26/06/2023 | Seven (7) risk and Compliance governance Policies adopted by Council by 30/06/2024 | N/A | N/A | N/A | N/A | Seven (7) risk and Compliance governance Policies adopted by Council by 30/06/2024 | N/A | N/A | N/A | N/A | N/A | N/A | Office of the MM | OPEX | Council resolution and Policies
MTID08 |  | Ensure functionality of Risk Management Committee | 8 | Number of Risk Committee meetings held by 30 June 2024 | Number meetings | n/a | New Indicator | New Indicator | Four (4) Risk Committee meetings held by 30 June 2024 | One (1) Risk Committee meetings held by 30/09/2023 | Zero (0) Risk Committee meetings held by 30/09/2023 | One (1) Risk Committee meetings held by 31 December 2023 | One (1) Risk Committee meetings held by 31 March 2024 | One (1) Risk Committee meetings held by 30 June 2024 | One (1) Risk Committee meetings held on the 17 October 2023 | Two (2) Risk Committee meetings held by 31 December 2023 | One (1) Risk Committee meetings held on the 17 October 2023 | Not Achieved | The Risk Chairperson was appointed by Council during the first Quarter. | The Risk Committee meeting was then scheduled for the 17 October 2023 | Office of the MM | OPEX | Notice,Agenda, Attandance Register, Minutes
MTID09 | To Improve organisational Capacity | Review of organisational structure | 9 | Date of organizational structure reviewed and adopted by Council by 31/05/2024 | Date of review and adoption | n/a | Review and adoption of organizational structure by Council by 30/06/2023 | Organizational structure reviewed and adopted by Council by 28/05/2023 | Review and adoption of organizational structure by Council by 31/05/2024 | N/A | N/A | N/A | N/A | Review and adoption of organizational structure by Council by 31/05/2024 | N/A | N/A | N/A | N/A | N/A | N/A | Corporate Services | OPEX | Council Resolution
MTID10 |  | Ensure implementation of Employment equity plan | 10 | Number of people from employment equity target groups employed in the three highest levels of management in compliance with approved equity plan by 30/06/2024 | Number of people | n/a | 2 people from employment equity target groups employed in the three (3)highest levels of management in compliance with approved equity plan by 30/06/2023 | 1 person from employment equity target groups employed in the three (3) highest levels of management in compliance with approved equity plan by 30/06/2023 | 1 person from employment equity target groups employed in the three (3) highest levels of management in compliance with approved equity plan by 30/06/2024 | N/A | N/A | N/A | N/A | 1 person from employment equity target groups employed in the three (3) highest levels of management in compliance with approved equity plan by 30/06/2024 | N/A | N/A | N/A | N/A | N/A | N/A | Corporate Services | OPEX | Employment Equity Plan and appointment letters
MTID11 |  | Implementation of Workplace Skills Plan | 11 | Percentage of budget spent in the implementation of Workplace Skills Plan by 30/06/2024 | Percentage of budget spent | n/a | Hundred (100%) of budget spent in the implementation of Workplace Skills Plan by 30/06/2023 | Fifty Five (55%) of budget spent in the implementation of Workplace Skills Plan by 30/06/2023 | Hundred (100%) of budget spent in the implementation of Workplace Skills Plan by 30/06/2024 | Twenty (25%) of budget spent in the implementation of Workplace Skills Plan by 30/09/2023 | Zero (0%) of budget spent in the implementation of Workplace Skills Plan by 30/09/2023 | Fifty (50%) of budget spent in the implementation of Workplace Skills Plan by 31/12/2023 | Seventy Five (75%) of budget spent in the implementation of Workplace Skills Plan by 31/03/2024 | Hundred (100%) of budget spent in the implementation of Workplace Skills Plan by 30/06/2024 | 8.8% of budget spent in the implementation of Workplace Skills Plan by 31/12/2023 | Fifty (50%) of budget spent in the implementation of Workplace Skills Plan by 31/12/2023 | 8.8% of budget spent in the implementation of Workplace Skills Plan by 31/12/2023 | Not Achieved | LGSeta has not yet disembursed Mandatory Grants payments | Upon receipt of Mandatory grants, training interventions will be implemented | Corporate Services | OPEX | Financial System Print Out
MTID12 |  |  | 12 | Number of training reports submitted to Council by 30/06/2024 | Number of training reports | n/a | New Indicator | New Indicator | 4 Training reports submitted to Council by 30/06/2024 | 1 Training report submitted to Council by 30/09/2023 | 1 Training report submitted to Council by 30/09/2023 | 1 Training report submitted to Council by 31/12/2023 | 1 Training report submitted to Council by 31/03/2024 | 1 Training report submitted to Council by 30/06/2024 | Zero (0) Training report submitted to Council by 31/12/2023 | 2 Training report submitted to Council by 31/12/2023 | 1 Training report submitted to Council by 31/12/2023 | Not Achieved | The Quarter 2 Training report submitted has not been tabled to Council | Reports will be submitted on the next Council sitting which is 29 February 2024 | Corporate Services | OPEX | Signed Reports to Council
MTID13 | To ensure an effective and efficient HR systems that addresses Human resources within the municipality | Review and adoption of HR related policies | 13 | Date to review and adopt HR related policies by Council by 30/06/2024 | Date of review and adoption | n/a | Review and adoption of HR related policies by Council by 30/06/2023 | HR related policies reviewed and adopted by Council on the 28/05/2023 | Review and adopt HR related policies by Council by 31/05/2024 | N/A | N/A | N/A | Review and adopt HR related policies by Council by 31/05/2024 | n/a | N/A | N/A | N/A | N/A | N/A | N/A | Corporate Services | OPEX | HR related policies & Council Resolution
MTID14 | To improve Information and Communication Technology through implementation of ICT policies | Development and review of ICT policies | 14 | Number of ICT Policies developed and reviewed by the Council by the 30th June 2024 | Number of Policies | n/a | New Indicator | New Indicator | Ten (10) ICT Policy reviewed by Council by 30/06/2024 | N/A | N/A | N/A | N/A | Ten (10) ICT Policy reviewed by Council by 30/06/2024 | N/A | N/A | N/A | N/A | N/A | N/A | Corporate Services | OPEX | Council Resolution,ICT Plicies
MTID15 | Ensure an effective and functional Fleet Services | Conducting Comprehensive reporting of Fleet Management Services | 15 | Number of Comprehensive Fleet Reports submitted to Council by 30/06/2024 | Number of reports | n/a | New Indicator | New Indicator | Four (4) of Comprehensive Fleet Reports submitted to Council by 30/06/2024 | One (1) of Comprehensive Fleet Reports submitted to Council by 30/09/2023 | One (1) of Comprehensive Fleet Reports submitted to Council by 30/09/2023 | One (1) of Comprehensive Fleet Reports submitted to Council by 31/12/2023 | One(1) of Comprehensive Fleet Reports submitted to Council by 31/03/2024 | One (1) of Comprehensive Fleet Reports submitted to Council by 20/06/2024 | One (1) of Comprehensive Fleet Reports submitted to Council by 31/12/2023 | Two (2) of Comprehensive Fleet Reports submitted to Council by 31/12/2023 | One (1) of Comprehensive Fleet Reports submitted to Council by 31/12/2023 | Not Achieved | The Quarter 2 Comprehensive Fleet Reports has not been tabled to Council | Reports will be submitted on the next Council sitting which is 29 February 2024 | Corporate Services | OPEX | Signed Reports
MTID16 | To ensure effective and efficient internal and external communication strategy. | Review and impelemtation of adopted Communication Strategy | 16 | Date of review and adoption of communication strategy by Council by 30/06/2024 | Date of review and adoption | n/a | Review and adotion of communication strategy by Councl by 30/06/2023 | Communication strategy was reviewed and adopted by Council on 26/06/2023 | Review and adoption of communication strategy by Councl by 30/06/2024 | N/A | N/A | N/A | N/A | Review and adoption of communication strategy by Councl by 30/06/2024 | N/A | N/A | N/A | N/A | N/A | N/A | Office of the MM | OPEX | Communication Strategy & Council Resolution
MTID17 | Improve communications with external Stakeholders | Development of Municipal Communication Strategy | 17 | Number of Municipal Newsletters published for each financial year by 30 June 2024 | Number of Newsletters | n/a | New Indicator | New Indicator | Four (4) Municipal newsletters published by 30/06/2024 | One (1) Municipal newsletters published by 30/09/2023 | One (1) Municipal newsletters published by 30/09/2023 | One (1) Municipal newsletters published by 31/12/2023 | One (1) Municipal newsletters published by 31/03/2024 | One (1) Municipal newsletters published by 30/06/2024 | One (1) Municipal newsletters published by 31/12/2023 | Two (2) Municipal newsletters published by 31/12/2023 | Two (2) Municipal newsletters published by 31/12/2023 | Achieved | N/A | N/A | Office of the MM |  | Municipal newsletters,Proof ofPublication
MTID18 | To report & monitor Service Delivery | Submission of quarterly reports to COGTA | 18 | Number of Circular 88 reports submitted to Provincial COGTA by 30/06/2024 | Number of reports | n/a | 4 Comprehensive Quarterly Performance Reports submitted to Provincial COGTA by 30/06/2023 | 4 Comprehensive Quarterly Performance Reports submitted to Provincial COGTA by 30/06/2023 | 4 Circular 88 reports submitted to Provincial COGTA by 30/06/2024 | 1 Circular 88 reports submitted to Provincial COGTA by 30/09/2023 | 1 Circular 88 reports submitted to Provincial COGTA by 30/09/2023 | 1 Circular 88 reports submitted to Provincial COGTA by 31/12/2023 | 1 Circular 88 reports submitted to Provincial COGTA by 31/03/2024 | 1 Circular 88 reports submitted to Provincial COGTA by 30/06/2024 | 1 Circular 88 reports submitted to Provincial COGTA by 31/12/2023 | Two (2) Circular 88 reports submitted to Provincial COGTA by 31/12/2023 | Two (2) Circular 88 reports submitted to Provincial COGTA by 31/12/2023 | Achieved | N/A | N/A | Office of the MM | OPEX | Circular 88 reports , Proof of submission
MTID19 | To improve the municipal Audit opinion | Effective Audit and Performance Committee | 19 | Number of Audit and Performance Committee meetings held by 30/06/2024 | Number of meetings | n/a | 4 Audit and Performance Committee meetings held by 30/06/2023 | 4 Audit and Performance Committee meetings held by 30/06/2023 | 4 Audit and Performance Committee meetings held by 30/06/2024 | 1 Audit and Performance Committee meeting held by 30/09/2023 | 3 Audit and Performance Committee meeting held by 30/09/2023 | 1 Audit and Performance Committee meeting held by 31/12/2023 | 1 Audit and Performance Committee meeting held by 31/03/2024 | 1 Audit and Performance Committee meeting held by 30/06/2024 | Two (2) Audit and Performance Committee meeting held on the 19 October 2023 & 13 December 2923 | 1 Audit and Performance Committee meeting held by 31/12/2023 | Five (5) Audit and Performance Committee meeting held on the 19 October 2023 & 13 December 2923 | Achieved | N/A | N/A | Office of the MM | OPEX | Minutes with attendance registers
MTID20 |  | Oversight meetings held | 20 | Number of MPAC meetings convened by 30/06/2024 | Number of meetings | n/a | 4 MPAC meetings convened by 30/06/2023 | 4 MPAC meetings convened by 30/06/2023 | 4 MPAC meetings convened by 30/06/2024 | 1 MPAC meeting convened by 30/09/2023 |  | 1 MPAC meeting convened by 31/12/2023 | 1 MPAC meeting convened by 31/03/2024 | MPAC meeting convened by 30/03/2024 | [6 empty] | Office of the MM | OPEX | Minutes with attendance registers
KPA2: BASIC SERVICE DELIVERY
BSD01 |  |  | 21 | Number of Households provided with water to eridicate backlock by 30/06/2024 | Number | Various | 1743 of Households provided with water to eridicate backlock by 30/06/2023 | 1743 of Households provided with water to eridicate backlock by 30/06/2023 | 750 of Households provided with water to eridicate backlock by 30/06/2024 | N/A | N/A | 400 of Households provided with water to eridicate backlock by 31/12/2023 | 350 | N/A | 400 of Households provided with water to eridicate backlock by 31/12/2023 | 400 of Households provided with water to eridicate backlock by 31/12/2023 | 0 of Households provided with water to eridicate backlock by 31/12/2023 | Not Achieved | The service provider/Consultant suspended works due to the poor perfomance of the contractor | A discussion of a session to be done in order for a reputable contractor to finish off the works, or an option to terminate the current contractor and appoint a new one to finish off the works is considered | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report, Beneficiary listing and Happy letters
BSD02 | To provide infrastructure and sustainable basic services | Provide community water supply | 22 | Number of Water treatment plant constructed at Bergvile WTW to be completed by 30/06/2024 | Number | 11 | New Indicator | New Indicator | (1)Number of sedimantation tank constructed at Bergvile WTW to be completed by 30/06/2024 | N/A | N/A | N/A | (1)Number sedimantation tank constructed at Bergvile WTW to be completed by 31/03/2024 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD03 |  |  | 23 | Number of KM's of bulk rising main pipeline constructed at Bergville WTW by 30/06/2024 | Number | 11 | New Indicator | New Indicator | 1.2 kilometers of bulk rising main pipeline constructed at Bergville WTW by 30/06/2024 | N/A | N/A | 0,6 kilometers of bulk pipeline to be constructed by 31/12/2023 | 0,6 kilometers of bulk pipeline to be constructed by 31/03/2023 | N/A | 1,056km | 0,6 kilometers of bulk pipeline to be constructed by 31/12/2023 | 1,056km kilometers of bulk pipeline to be constructed by 31/12/2023 | Achieved | The contractor has over achieved | The contractor has adhered to the programme of works submitted. | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD04 |  |  | 24 | Date of Appointment of Contractor at Colenso and Rosboom Bulk Water:Phase 2 to be completed by 30/06/2024 | Date of appointment | 25 | New Indicator | New Indicator | Appointment of Contractor at Colenso and Rosboom Bulk Water:Phase 2 to be completed by 30/06/2024 | N/A | N/A | N/A | N/A | Appointment of Contractor at Colenso and Rosboom Bulk Water:Phase 2 to be completed by 30/06/2024 | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD05 |  |  | 25 | Number of bulk pipeline constructed at Ezakheni WCDM: Phase 2 by 30/06/2024 | Number of kilometers | 1,2,3,4,5,8,13 & 20 | New Indicator | New Indicator | 1,03 km of bulk pipeline constructed at Ezakheni WCDM Phase 2 by 30/06/2024 | N/A | N/A | 0,28 kilometers of bulk pipelines to be constructed by 31/12/2023 | 0,49 kilometers of bulk pipeline to be constructed by 31/03/2024 | 0,26 kilometers of bulk pipeline to be constructed by 30/06/2024 | 0 kilometers of bulk pipelines to be constructed by 31/12/2023 | 0,28 kilometers of bulk pipelines to be constructed by 31/12/2023 | 0 kilometers of bulk pipelines to be constructed by 31/12/2023 | Not Achieved | Late appointment of service providers/ Delays in SCM processes | Appointment of contractor has been done and to resume works on site in January 2024 | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD06 |  |  | 26 | Number of Bulk meters to be installed at Ezakheni WCDM: Phase 2 by 30/06/2023 | Number | 1,2,3,4,5,8,13 & 20 | New Indicator | New Indicator | 12 Bulk meters to be installed at Ezakheni WCDM: Phase 2 by 30/06/2023 | N/A | N/A | N/A | 6 Bulk meters to be installed by 31/03/2024 | 6 Bulk meters to be installed by 30/06/2024 | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD07 |  |  | 27 | Date of Completion of Designs at KwaMkhize Bulk Water Supply and Reticulation Network by 30/06/2024 | Date of completion | 11 & 12 | New Indicator | New Indicator | Completion of Designs at KwaMkhize Bulk Water Supply and Reticulation Network by 30/06/2024 | N/A | N/A | N/A | N/A | Completion of Designs at KwaMkhize Bulk Water Supply and Reticulation Network by 30/06/2024 | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD08 |  |  | 28 | Date of Site Completion of site establishment at Langkloof and Bulk Supply:Phase 1 by 30/09/2023 | Date of completion | 10 | New Indicator | New Indicator | Completion of site establishment at Langkloof and Bulk Supply:Phase 1 by 30/09/2023 | Completion of site establishment at Langkloof and Bulk Supply:Phase 1 by 30/09/2023 | The site establishment at Langkloof and Bulk Supply:Phase 1 was not completed by 30/09/2023 | N/A | N/A | N/A | N/A | Completion of site establishment at Langkloof and Bulk Supply:Phase 1 by 30/09/2023 | The site establishment at Langkloof and Bulk Supply:Phase 1 was not completed by 30/09/2023 | Not Achieved | SCM process delayed the appointment of the Contractor.Project hand over occurred on the 10th October 2023 | Contractor to prepare all contractrual documents and to commence with works by 31 October 2023 | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD09 |  |  | 29 | Number of km reticulation pipelines constructed in Langkloof Package Plant and Bulk Supplyby 30/06/2024 | Number of Kilometers | 10 | New Indicator | New Indicator | 7,7 km reticulation pipeline to be constructed at Langkloof Package Plant by 30/06/2024 | N/A | N/A | 2 km reticulation pipeline to be constructed at Langkloof Package Plant by 31/12/2023 | 2 km reticulation pipeline to be constructed at Langkloof Package Plant by 31/03/2024 | 3,7 km reticulation pipeline to be constructed at Langkloof Package Plant by 30/06/2024 | 0 km reticulation pipeline to be constructed at Langkloof Package Plant by 31/12/2023 | 2 km reticulation pipeline to be constructed at Langkloof Package Plant by 31/12/2023 | 0 km reticulation pipeline to be constructed at Langkloof Package Plant by 31/12/2023 | Not Achieved | Delays in the appointment of contractor | Contractor has been appointed and is currently on site | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD10 |  |  | 30 | Number of Kilometers of reticulation pipelines constructed at Ennersdale/ Ephangwini(Loskop) ward 4 by 30/09/2024 | Number of Kilometers | 4 | New Indicator | New Indicator | 1 km of reticulaton to be constructed at Ennersdale/Ephangwini ward 4 by 30/09/2023 | 1 km of reticulaton to be constructed at Ennersdale/Ephangwini ward 4 by 30/09/2023 | 0,6 km of reticulaton constructed at Ennersdale/Ephangwini ward 4 by 30/09/2023 | N/A | N/A | N/A | N/A | 1 km of reticulaton to be constructed at Ennersdale/Ephangwini ward 4 by 30/09/2023 | 0,6 km of reticulaton constructed at Ennersdale/Ephangwini ward 4 by 30/09/2023 | Not Achieved | Contractor suspended works on site due to financial constraints | UTDM have instructed the Consultant to issue an intention to terminate to the Contractor. | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD11 |  |  | 31 | Date of Completion of winterton sanitation designs by 31/03/2024 | Date of completion | 1 | New Indicator | New Indicator | Completion of sanitation designs at Winterton by 31/03/2024 | N/A | N/A | N/A | N/A | Completion of sanitation designs at Winterton by 30/06/2024 | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD12 |  |  | 32 | Completion of winterton water supply designs by 30/06/2024 | Date of completion | 1 | New Indicator | New Indicator | Completion of winterton water supply designs by 30/06/2024 | N/A | N/A | N/A | N/A | Completion of winterton water supply designs by 30/06/2024 | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD13 |  |  | 33 | Number district wide springs protected by 30/06/2024 | Number | Various | Twelve (12) district wide springs protected by 30/06/2024 | Twelve (12) district wide springs protected by 30/06/2024 | 12 spring protected district wide by 30/06/2024 | 3 Springs protection were constructed by 30/09/2023 | 3 springs protected district wide were constructed by 30/09/2023 | 3 springs protected district wide constructed by 31/12/2023 | 0 springs protected district wide 31/12/2023 | 3 springs protected district wide 31/12/2023 | 0 springs protected district wide constructed by 31/12/2023 | 3 springs protected district wide constructed by 31/12/2023 | 0 springs protected district wide constructed by 31/12/2023 | Not Achieved | Change of scope was undertaken due prioritizing extensions of reticulation on the existing spring | Outstanding springs will be included in the new business plan,BP awaiting approval | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD14 |  |  | 34 | Number of drilled and equiped boreholes district wide by 30/06/2024 | Number | Various | Ten (10) boreholes drilled and equipped | Ten (10) boreholes drilled and equipped | Ten (10) boreholes drilled and equipped by 30/06/2024 | 3 boreholes drilled and equipped district wide by 30/09/2023 | 0 boreholes drilled and equipped district wide by 30/09/2023 | 5 production boreholes to be equipped by 31/12/2023 | 3 boreholes drilled and equipped district wide | 1 boreholes drilled and equipped district wide | No (0) production boreholes equipped by 31/12/2023 | 5 production boreholes to be equipped by 31/12/2023 | No (0) production boreholes equipped by 31/12/2023 | Not Achieved | The boreholes that were drilled and tested were dry and could not produce enough water | Further extension of reticulation has beed done in the boreholes that were tested to provide a lrge number of beneficiaries with water | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD15 | To provide santitation system to the community | Provision and maintainance of sanitation infrastructure | 35 | Number of kilometers of Reticulation constructed at Fitty Park Community water project:Phase 2 by 30/06/2024 | Number of Kilometers | 7 & 28 | New Indicator | New Indicator | 13 Kilometers of reticulation pipeliens constructed at Fitty Park Community Water Project by 30/06/2024 | 2,3 km of reticulation to be constructed at Fitty Park Community Water Project by 30/09/2023 |  | 3,4 km of reticulation to be constructed at Fitty Park Community Water Project by 31/12/2024 | 3,7 km of reticulation to be constructed by 31/03/2024 | 3,6 km of reticulation to be constructed by 30/06/2024 | No (0km) reticulation was constructed at Fitty Park Community water project:Phase 2 by 31/12/2023 | 3,4 km of reticulation to be constructed at Fitty Park Community Water Project by 31/12/2024 | No (0km) reticulation was constructed at Fitty Park Community water project:Phase 2 by 31/12/2023 | Not Achieved | Contractor suspended works on site due to non payment | Contractor has been paid and has resumed work on site. The contractor to accelerate the works on site. | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD16 |  |  | 36 | Number of VIP toilets constructed by 30/06/2024 | Number | Various | New Indicator | New Indicator | 2000 VIP toilets constructed by 30/06/2024 | 500 VIP toilets constructed by 30/09/2023 |  | 500 VIP toilets constructed by 31/12/2023 | 500 VIP tiolets constructed by 31/03/2024 | 500 VIP toilets constructed by 30/06/2024 | 423 VIP toilet constructed by 31/12/2023 | 500 VIP toilets constructed by 31/12/2023 | 423 VIP toilet constructed by 31/12/2023 | Not Achieved | The contractor encountered social challenges | The contractor is within the programme of works | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Repor, Beneficiary listing and Happy letters
BSD17 | To provide infrastructure and sustainable basic services | Provide community water supply | 37 | Date of completion of designs of Fitty Park Umhlumayo Bulk water supply infrustructure upgrade Tugela Estate by 30/06/2024 | Date of completion | 7, 28, 29 & 30 | New Indicator | New Indicator | Date of completion of designs of Fitty Park Umhlumayo Bulk water supply infrustructure upgrade Tugela Estate by 30/06/2024 | N/A | N/A | N/A | N/A | Completion of designs of Fitty Park Umhlumayo Bulk water supply infrustructure upgrade Tugela Estate by 30/06/2024 | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD18 |  |  | 38 | Number of Kilometers of reticulation pipelines constructed at Okhahlamba LM (Ward 2,3 & 14) East Reticulation 01 by 30/06/2024 | Number of kilometers | 14 | New Indicator | New Indicator | 0,51 kilometers of reticulation pipeline to constructed at Okhahlamba LM (Ward 2,3 & 14) East Reticulation 01 by 30/06/2024 | 0.51 kilometers of reticulation pipeline to be constructed at Okhahlamba LM (Ward 2,3 & 14) East Reticulation 01 by 30/09/2023 | 0.51 kilometers of reticulation pipeline to be constructed at Okhahlamba LM (Ward 2,3 & 14) East Reticulation 01 by 30/09/2023 | N/A | N/A | N/A | N/A | 0.51 kilometers of reticulation pipeline to be constructed at Okhahlamba LM (Ward 2,3 & 14) East Reticulation 01 by 30/09/2023 | 0,51 kilometers of reticulation pipeline constructed at Okhahlamba LM (Ward 2,3 & 14) East Reticulation 01 by 30/09/2023 | Achieved | N/A | N/A | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD19 |  |  | 39 | Number of Kilometers of bulk pipelines constructed at Okhahlamba LM (Ward 2,3 & 14) East Reticulation 01 by 30/06/2024 | Number of kilometers | 14 | New Indicator | New Indicator | 0,6 of kilometers of bulk pipeline to constructed at Okhahlamba LM (Ward 2,3 & 14) East Reticulation 01 by 30/06/2024 | 0.4 kilometers of bulk pipeline to be constructed at Okhahlamba LM (Ward 2,3 & 14) East Reticulation 01 by 30/09/2023 | 0.5 kilometers of bulk pipeline to be constructed at Okhahlamba LM (Ward 2,3 & 14) East Reticulation 01 by 30/09/2023 | 0.2 kilometers of bulk pipeline to be constructed at Okhahlamba LM (Ward 2,3 & 14) East Reticulation 01 by 31/12/2023 | N/A | N/A | No (0km) kilometers of bulk pipeline was constructed at Okhahlamba LM (Ward 2,3 & 14) East Reticulation 01 by 31/12/2023 | 0.2 kilometers of bulk pipeline to be constructed at Okhahlamba LM (Ward 2,3 & 14) East Reticulation 01 by 31/12/2023 | No (0km) kilometers of bulk pipeline was constructed at Okhahlamba LM (Ward 2,3 & 14) East Reticulation 01 by 31/12/2023 | Not Achieved | The contractor has over achieved in the previous quarter | The contractor is within the programme | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD20 |  |  | 40 | Number of Reserviors constructed at Okhahlamba Ward 14 East by 31/03/2024 | Number | 14 | New Indicator | New Indicator | (1) Number of Reservior constructed at Okhahlamba Ward 14 East by 31/03/2024 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD21 |  |  | 41 | Number of Kilometers of reticulation pipelines Okhahlamba LM (Ward 2,3 & 14) West Reticulation 01 by 30/06/2024 | Number of Kilometers | 14 | New Indicator | New Indicator | 0,275 kilometers of reticulation pipeline to constructed by 30/06/2024 | 0.275 kilometers of reticulation pipeline to be constructed by 30/09/2023 | 0 kilometers of bulk pipeline not constructed at Okhahlamba LM (Ward 2,3 & 14) West Reticulation 01 by 30/09/2023 | N/A | N/A | N/A | N/A | 0.275 kilometers of reticulation pipeline to be constructed by 30/09/2023 | 0 kilometers of bulk pipeline not constructed at Okhahlamba LM (Ward 2,3 & 14) West Reticulation 01 by 30/09/2023 | Not Achieved | Contractor suspended works on site | Contractor has commenced works on site,Contractor will execute activities simultanteously to accelerate progress on site | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD22 |  |  | 42 | Number of Kilometers bulk pipelines Okhahlamba LM (Ward 2,3 & 14) West Reticulation 01 by 30/06/2024 | Number of kilometers | 14 | New Indicator | New Indicator | 0,7 of kilometers of bulk pipeline to constructed at Okhahlamba LM (Ward 2,3 & 14) West Reticulation 01 by 30/06/2024 | 0.5 kilometers of bulk pipeline to be constructed at Okhahlamba LM (Ward 2,3 & 14) West Reticulation 01 by 30/09/2023 | 0 kilometers of bulk pipeline not constructed at Okhahlamba LM (Ward 2,3 & 14) West Reticulation 01 by 30/09/2023 | 0.2 kilometers of bulk pipeline to be constructed at Okhahlamba LM (Ward 2,3 & 14) West Reticulation 01 by 31/12/2023 | N/A | N/A | No (0KM) kilometers of bulk pipeline was constructed at Okhahlamba LM (Ward 2,3 & 14) West Reticulation 01 by 31/12/2023 | 0.7 kilometers of bulk pipeline to be constructed at Okhahlamba LM (Ward 2,3 & 14) West Reticulation 01 by 31/12/2023 | No (0KM) kilometers of bulk pipeline was constructed at Okhahlamba LM (Ward 2,3 & 14) West Reticulation 01 by 31/12/2023 | Not Achieved | The contractor has over achieved in the previous quarter | The contractor is within the programme | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD23 |  |  | 43 | Number of Reserviors constructed at Okhahlamba Ward 14 West by 31/03/2024 | Number | 14 | New Indicator | New Indicator | (1) Number of Reservior constructed at Okhahlamba (Vimbikhalo)Ward 14 East by 31/03/2024 | N/A | N/A | (1) Number of Reservior constructed at Okhahlamba Ward 14 East by 31/03/2024 | N/A |  | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services |  | Signed Engineers Report
BSD24 |  |  | 44 | Number of production boreholes to be equipped at Okhahlamba by 30/06/2024 | Number | 2,3,14 | New Indicator | New Indicator | 10 production boreholes to be drilled at Okhahlamba by 30/06/2024 | 5 production boreholes to be equipped by 30/09/2023 | 0 production boreholes to be equipped by 30/09/2023 | 5 production boreholes to be equipped by 31/12/2023 | N/A | N/A | 0 production boreholes to be equipped by 31/12/2023 | 10 production boreholes to be equipped by 31/12/2023 | No (0) production boreholes equipped by 31/12/2023 | Not Achieved | The boreholes that were drilled and tested were dry and could not produce enough water | Further extension of reticulation has beed done in the boreholes that were tested to provide a lrge number of beneficiaries with water | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD25 |  |  | 45 | Number of handpumps to be equipped at Okhahlamba by 30/06/2024 | Number | 2,3,14 | New Indicator | New Indicator | 33 handpummps to be drilled at Okhahlamba by 30/06/2021 | 17 handpumps to be equipped by 30/09/2023 | 9 handpumps to be equipped by 30/09/2023 | 3 handpumps to be equipped by 31/12/2023 | N/A | N/A | 33 handpumps equipped by 31/12/2023 | 33 handpumps to be equipped by 31/12/2023 | 12 handpumps equipped by 31/12/2023 | Not Achieved | The boreholes that were drilled and tested and the water quality was not fit for human consumption | further tests to be done to look into options of purifying the water for human consumption | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD26 |  |  | 46 | Appointment of 2 Contractors at Okhahlamba (Vimbukhalo) by 31/03/2024 | Date | 14 | New Indicator | New Indicator | Appointment of Contractor at Okhahlamba (Vimbukhalo) Ward (14) by 31/03/2024 | N/A | N/A | N/A | Appointment of Contractor at Okhahlamba (Vimbukhalo) by 31/03/2024 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD27 |  |  | 47 | Number of bulk pipeline constructed at Steadville WCDM by 30/06/2024 | Number of Kilometers | 9 & 10 | New Indicator | New Indicator | 7 kilometers of bulk pipeline constructed at Steadville WCDM by 30/06/2024 | N/A | N/A | 2 km of bulk pipeline to be constructed at Steadville WCDM by 31/12/2023 | 2 km of bulk pipeline to constructed by 31/03/2024 | 3 km of bulk pipeline to be constructed by 30/06/2024 | 2 km of bulk pipeline to be constructed at Steadville WCDM by 31/12/2023 | 2 km of bulk pipeline to be constructed at Steadville WCDM by 31/12/2023 | 0 km of bulk pipeline to be constructed at Steadville WCDM by 31/12/2023 | Not Achieved | Late appointment of service providers/ Delays in SCM processes | Appointment of contractor has been done and to resume works on site in January 2024 | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD28 |  |  | 48 | Number of installation of bulk metering at Steadville WCDM by 30/06/2024 | Number | 9 & 10 | New Indicator | New Indicator | (5) installation of bulk metering at Steadville by 30/06/2024 | N/A | N/A | 2 bulk meters to be installed by 31/12/2023 | 3 bulk meters to be installed by 31/03/2024 | N/A | 0 bulk meters to be installed by 31/12/2023 | 2 bulk meters to be installed by 31/12/2023 | 3 bulk meters to be installed by 31/03/2024 | Not Achieved | Late appointment of service providers/ Delays in SCM processes | Appointment of contractor has been done and to resume works on site in January 2024 | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD29 |  |  | 49 | Number of bulk pipeline constructed at Ladysmith AC pipeline replacement by 30/06/2024 | Number of Kilometers | 12 | New Indicator | New Indicator | 10 kilometers of bulk pipeline constructed at Ladysmith AC pipeline replacement | N/A | N/A | 2 km of bulk pipeline to be constructed by 31/12/2023 | 4 km of bulk pipeline to constructed by 31/03/2024 | 4 km of bulk pipeline to be constructed by 30/06/2024 | 0 km of bulk pipeline to be constructed by 31/12/2023 | 2 km of bulk pipeline to be constructed by 31/12/2023 | 0 km of bulk pipeline to be constructed by 31/12/2023 | Not Achieved | Late appointment of service providers/ Delays in SCM processes | Appointment of contractor has been done and to resume works on site in January 2024 | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD30 |  |  | 50 | Number of installation of bulk metering at Ladysmith AC pipeline replacement by 30/06/2024 | Number | 12 | New Indicator | New Indicator | (5) installation of bulk metering at Ladysmith AC pipeline replacement by 30/06/2024 | N/A | N/A | 2 bulk meters to be installed by 31/12/2023 | 3 bulk meters to be installed by 31/03/2024 | N/A | 0 bulk meters to be installed by 31/12/2023 | 2 bulk meters to be installed by 31/12/2023 | 0 bulk meters to be installed by 31/12/2023 | Not Achieved | Late appointment of service providers/ Delays in SCM processes | Appointment of contractor has been done and to resume works on site in January 2024 | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD31 |  |  | 51 | Number of KM's of UPVC Mains constructed at KwaNobamba/Ezitendeni Water Supply by 30/06/2024 | Number of Kilometers | 21 | New Indicator | New Indicator | 0,3 Km's of UPVC Mains to be constructed at KwaNobamba/Ezitendeni Water Supply by 20/07/2023 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | CAPEX | Signed Engineers Report
BSD32 | To ensure safe and healthy potable water | Implement an effective water and waste water monitoring program | 52 | Number of water treatment plants monitred by 30/06/2024 | Number | n/a | 15 water treatment plants monitored by 30/06/2023 | 15 water treatment plants monitored by 30/06/2023 | 15 water treatment plants monitored by 30/06/2024 | 15 water treatment plants monitored by 30/09/2023 | 15 water treatment plants monitored by 30/09/2023 | 15 water treatment plants monitored by 31/12/2023 | 15 water treatment plants monitored by 31/03/2024 | 15 water treatment plants monitored by 30/06/2024 | 15 water treatment plants monitored by 31/12/2023 | 15 water treatment plants monitored by 31/12/2023 | 15 water treatment plants monitored by 31/12/2023 | Achieved | N/A | N/A | Community Services | CAPEX | Signed reports
BSD33 |  |  | 53 | Number of waste water treatment works monitored by 30/06/2024 | Number | n/a | 9 waste water treatment works monitored by 30/06/2023 | 9 waste water treatment works monitored by 30/06/2023 | 9 waste water treatment works monitored by 30/06/2024 | 9 waste water treatment works monitored by 30/09/2022 | 9 waste water treatment works monitored by 30/09/2022 | 9 waste water treatment works monitored by 31/12/2022 | 9 waste water treatment works monitored by 31/03/2023 | 9 waste water treatment works monitored by 30/06/2023 | 9 waste water treatment works monitored by 31/12/2022 | 9 waste water treatment works monitored by 31/12/2022 | 9 waste water treatment works monitored by 31/12/2022 | Achieved | N/A | N/A | Community Services | OPEX | Signed reports
BSD34 | To enhance consumer protection with sufficient food control | Monitor compliance of food sellling outlets | 54 | Number of food handling premises inspected by 30/06/2024 | Number | n/a | 864 food handling premises inspected by 30/06/2023 | 864 food handling premises inspected by 30/06/2023 | 864 food handling premises inspected by 30/06/2024 | 216 food handling premises inspected by 30/09/2023 | 216 food handling premises inspected by 30/09/2023 | 216 food handling premises inspected by 31/12/2023 | 216 food handling premises inspected by 31/03/2024 | 216 food handling premises inspected by 30/06/2024 | 216 food handling premises inspected by 31/12/2023 | 432 food handling premises inspected by 31/12/2023 | 626 food handling premises inspected by 31/12/2023 | Achieved | N/A | N/A | Community Services | OPEX | Signed reports
LOCAL ECONOMIC DEVELOPMENT
LED01 | To Increase Job opportunities | Implement Expanded Public Works Programme (EPWP) | 55 | Number of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2024 | Number of EPWP jobs | District -wide | 1019 of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2023 | 849 of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2023 | 1032 of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2024 | N/A | N/A | N/A | N/A | 1032 of EPWP jobs created through LED initiatives, including capital projects, by 30/06/2024 | N/A | N/A | N/A | N/A | N/A | N/A | Water, Sanitation & Technical Services | EPWP GRANT | Signed reports
LED02 |  |  | 56 | Number of EPWP reports submitted to the funder by 30/06/2024 | Number of EPWP reports | District -wide | New Indicator | New Indicator | 12 EPWP reports submitted to the funder by 30/06/2024 | 3 EPWP reports submitted to the funder by 30/09/2023 | 3 EPWP reports submitted to the funder by 30/09/2023 | 3 EPWP reports submitted to the funder by 31/12/2023 | 3 EPWP reports submitted to the funder by 31/03/2024 | 3 EPWP reports submitted to the funder by 30/06/2024 | 3 EPWP reports submitted to the funder by 31/12/2023 | 6 EPWP reports submitted to the funder by 31/12/2023 | 6 EPWP reports submitted to the funder by 31/12/2023 | Achieved | N/A | N/A | Water, Sanitation & Technical Services | OPEX | Signed reports
LED03 |  | Convene district LED/Tourism Forum meetings | 57 | Number of disrtict LED/Tourism forums meetings held by 30/06/2024 | Number of meetings | n/a | New Indicator | New Indicator | 4 disrtict LED/Tourism forums meetings held by 30/06/2024 | 1 disrtict LED/Tourism forums meeting held by 30/09/2023 |  | 1 disrtict LED/Tourism forum meetings held by 31/12/2023 | 1 disrtict LED/Tourism forum meetings held by 31/03/2024 | 1 disrtict LED/Tourism forum meetings held by 30/06/2024 | 1 disrtict LED/Tourism forum meetings held by 31/12/2023 | Two (2) disrtict LED/Tourism forum meetings held by 31/12/2023 | Two (2) disrtict LED/Tourism forum meetings held by 31/12/2023 | Achieved | N/A | N/A | Social and Economic Services | OPEX | Signed reports
KPA 4: GOOD GOVERNANCE & PUBLIC PARTICIPATION
GGPP01 | To ensure good and effective governance | Participate the IGR Structures | 58 | % of functional IGR Structures by 30/06/2024 | Percentage of fuctional structures | n/a | New Indicator | New Indicator | 100% of functional IGR Structures by 30/06/2024 | 100% of functional IGR Structures by 30/09/2024 | 100% of functional IGR Structures by 30/09/2024 | 100% of functional IGR Structures by 31/12/2024 | 100% of functional IGR Structures by 31/03/2024 | 100% of functional IGR Structures by 30/06/2024 | 100% of functional IGR Structures by 31/12/2024 | 100% of functional IGR Structures by 31/12/2024 | 100% of functional IGR Structures by 31/12/2024 | Achieved | N/A | N/A | Office of the MM | OPEX | Notice, minutes & attendance registers
GGPP02 | To promote the interest of designated groups | Participate in the annual programmes | 59 | Number of Special Programmes targeting designated groups co-ordinated and participating in within the district by 30/06/2024 | Number of special programmes | All | 7 Special Programmes targeting designated groups co-ordinated and participating in within the district by 30/06/2023 | 8 Special Programmes targeting designated groups co-ordinated and participating in within the district by 30/06/2023 | 7 Special Programmes targeting designated groups co-ordinated and participating in within the district by 30/06/2024 | N/A | N/A | N/A | 1 Special Programme targeting designated groups co-ordinated and participating in within the district by 31/03/2024 | 2 Special Programmes targeting designated groups co-ordinated and participating in within the district by 30/06/2024 | N/A | N/A | N/A | N/A | N/A | N/A | Office of the MM | OPEX | Signed Reports
KP5: MUNICIPAL FINANCIAL VIABILITY AND MANAGEMENT
MFVM01 | To ensure legally sound financial viability and management | Timeous financial reporting and management | 60 | Percentange of MIG Expenditure by 30/06/2024 | Percentage of exependiture | n/a | 100% of MIG expenditure by 30/06/2023 | 100% of MIG expenditure by 30/06/2023 | 100% of MIG expenditure by 30/06/2024 | 25% of MIG expenditure by 30/09/2023 | 25% of MIG expenditure by 30/09/2023 | 50% of MIG expenditure by 31/12/2023 | 75% of MIG expenditure by 31/03/2024 | 100% of MIG expenditure by 30/06/2024 | 49% of MIG expenditure by 31/12/2023 | 50% of MIG expenditure by 31/12/2023 | 49% of MIG expenditure by 31/12/2023 | Not Achieved | Late appointment of service providers/ Delays in SCM processes | UTDM Has appointed service providers to resume works on site. | Water, Sanitation & Technical Services | MIG | Grant exenditure report and proof of payments
MFVM02 |  |  | 61 | Percentange of annual allocation to free basic services spent by 30/06/2024 | Percentage spent | n/a | 100% of annual allocation to free basic services spent by 30/06/2023 | 0% of annual allocation to free basic services spent by 30/06/2023 | 100% of annual allocation to free basic services spent by 30/06/2024 | 25% of annual allocation to free basic services spent by 30/09/2023 | 0% of annual allocation to free basic services spent by 30/09/2023 | 50% of annual allocation to free basic services spent by 31/12/2023 | 75% of annual allocation to free basic services spent by 31/03/2024 | 100% of annual allocation to free basic services spent by 30/06/2024 | 46% of annual allocation to free basic services spent by 31/12/2023 | 50% of annual allocation to free basic services spent by 31/12/2023 | 46% of annual allocation to free basic services spent by 31/12/2023 | Not Achieved |  |  | Budget & Treasury Office | OPEX | Signed reports
MFVM03 |  |  | 62 | Percentage of operating budget spent by 30/06/2024 | Percentage spent | n/a | 100% of operating budget spent by 30/06/2023 | 74% of operating budget spent by 30/06/2023 | 100% of operating budget spent by 30/06/2024 | 25% of operating budget spent by 30/09/2023 | 62% of operating budget spent by 30/09/2023 | 50% of operating budget spent by 31/12/2023 | 75% of operating budget spent by 31/03/2024 | 100% of operating budget spent by 30/06/2024 | 34,2 % of operating budget spent by 31/12/2023 | 50% of operating budget spent by 31/12/2023 | 34,2 % of operating budget spent by 31/12/2023 | Not Achieved |  |  | Budget & Treasury Office | OPEX | Signed reports
MFVM04 |  |  | 63 | Percentange of capital budget spent by 30/06/2024 | Percentage spent | n/a | 100% of capital budget spent by 30/06/2023 | 100% of capital budget spent by 30/06/2023 | 100% of capital budget spent by 30/06/2024 | 25% of capital budget spent by 30/09/2023 | 25% of capital budget spent by 30/09/2023 | 50% of capital budget spent by 31/12/2023 | 75% of capital budget spent by 31/03/2024 | 100% of capital budget spent by 30/06/2024 | 46,6 % of capital budget spent by 31/12/2023 | 50% of capital budget spent by 31/12/2023 | 46,6 % of capital budget spent by 31/12/2023 | Not Achieved | Challenges on Slow Spending on projects Late appointments of Service Providers within the financial year | The Municipality will draft a mantainance plan. 2. Proper adherence to the Procurement Plan. 3. Close monitoring of projects | Budget & Treasury Office | CAPEX | Signed reports
MFVM05 |  |  | 64 | Percentange of repairs and maintenance spent by 30/06/2024 | Percentage spent | n/a | 100% of repairs and maintenance spent by 30/06/2023 | 38% of repairs and maintenance spent by 30/06/2011 | 100% of repairs and maintenance spent by 30/06/2024 | 25% of repairs and maintenance spent by 30/09/2023 | 2.45% of repairs and maintenance spent by 30/09/2023 | 50% of repairs and maintenance spent by 31/12/2023 | 75% of repairs and maintenance spent by 31/03/2024 | 100% of repairs and maintenance spent by 30/06/2024 | 13% of repairs and maintenance spent by 31/12/2023 | 50% of repairs and maintenance spent by 31/12/2023 | 13% of repairs and maintenance spent by 31/12/2023 | Not Achieved | The Repairs and maintainance budget is not as per the norm. The Municipality has unfunded budget are there are cash constraints. | 1. Development of the Maintenance Plan. | Budget & Treasury Office | OPEX | Signed reports
MFVM06 |  |  | 65 | Ratio on financial viability in terms of debt coverage by 30/06/2024 | Ratio | n/a | 1:03 | 8,49: 03 | 1:03 | 1:03 | 0.44:7 | 1:03 | 1:03 | 1:03 | 0,50:03 | 1:03 | 0,50:03 | Not Achieved | 1. Low Collection Rate 2.Installed smart meters not yielding results | 1. Implementation of the Revenue Enhancement Strategy. 2.Finalization of the matter between the Municipality and the installers of smart meters | Budget & Treasury Office | OPEX | Signed reports
MFVM07 |  |  | 66 | Ratio on financial viability in terms of cost coverage by 30/06/2024 | Ratio | n/a | 1:02 | 1,47: 02 | 1:02 | 1:02 | 3.8:22 | 1:02 | 1:02 | 1:02 | 0;04 | 1:02 | 0;04 | Not Achieved | 1. Low Collection rate. 2. Unfunded Budget | 1. Implementation of the Revenue Enhancement Strategy. 2. Preparation and implementation of the credible Budget Funding Plan with clear cost cutting measures | Budget & Treasury Office | OPEX | Signed reports
MFVM08 |  |  | 67 | Ratio on financial viability in terms of outstanding service debtors to revenue by 30/06/2024 | Ratio | n/a | 1:01 | 0,14: 01 | 1:01 | 1:01 | 3.8:22 | 1:01 | 1:01 | 1:01 | 5,7:01 | 1:01 | 5,7:01 | Not Achieved | 1. Low Collection rate. 2. Unfunded Budget | 1. Implementation of the Revenue Enhancement Strategy. 2. Preparation and implementation of the credible Budget Funding Plan with clear cost cutting measures | Budget & Treasury Office | OPEX | Signed reports
MFVM09 |  |  | 68 | Date of approval of 2024/2025 budget by 31/05/2024 | Date of approval | n/a | Approval of 2023/23 budget by 31/05/2022 | 2023/23 Budget was approved on the 28/05/2022 | Approval of 2023/24 budget by 31/05/2024 | N/A | N/A | N/A | N/A | Approval of 2024/24 budget by 31/05/2024 | N/A | N/A | N/A | N/A | N/A | N/A | Budget & Treasury Office | OPEX | Council resolution
MFVM10 |  |  | 69 | Number of Progress Reports Submitted to Provincial Treasury on Implementation of the Budget Funding Plan by 30 June 2023 | Number |  | New Indicator | New Indicator | Twelve (12) of Progress Reports Submitted to Provincial Treasury on Implementation of the Budget Funding Plan by 30 June 2023 | Three (03) of Progress Reports Submitted to Provincial Treasury on Implementation of the Budget Funding Plan by 30 September 2023 | Three (03) of Progress Reports Submitted to Provincial Treasury on Implementation of the Budget Funding Plan by 30 September 2023 | Three (3) of Progress Reports Submitted to Provincial Treasury on Implementation of the Budget Funding Plan by 31 December 2023 | Three (3) of Progress Reports Submitted to Provincial Treasury on Implementation of the Budget Funding Plan by 31 March 2024 | Three (3) of Progress Reports Submitted to Provincial Treasury on Implementation of the Budget Funding Plan by 30 June 2024 | Three (3) of Progress Reports Submitted to Provincial Treasury on Implementation of the Budget Funding Plan by 31 December 2023 | Six (6) of Progress Reports Submitted to Provincial Treasury on Implementation of the Budget Funding Plan by 31 December 2023 | Six (6) of Progress Reports Submitted to Provincial Treasury on Implementation of the Budget Funding Plan by 31 December 2023 | Achieved | N/A | N/A | Budget & Treasury Office | OPEX | Progress Reports, Proof of Submission to Treasury
MFVM11 |  |  | 70 | Date of submission of credible Annual Financial Statements to the Auditor-Genral by 31/08/2023 | Date of submission | n/a | Submission of credible Annual Financial Statements to the Auditor-Genral by 31/08/2022 | Submitted credible Annual Financial Statements to the Auditor-Genral by 31/10/2022 | Submission of credible Annual Financial Statements to the Auditor-Genral by 31/08/2023 | Submission of credible Annual Financial Statements to the Auditor-Genral by 31/08/2023 | The credible Annual Financial Statements were submitted to the Auditor-General by 31/08/2023 | N/A | N/A | N/A | N/A | Submission of credible Annual Financial Statements to the Auditor-Genral by 31/08/2023 | The credible Annual Financial Statements were submitted to the Auditor-General by 31/08/2023 | Achieved | N/A | N/A | Budget & Treasury Office | OPEX | Proof of submission and Annual Financial Statements
MFVM12 |  | Ensure legislative compliance | 71 | Number of Asset Register developed by 30/06/2024 | Number of registers | n/a | 1 Asset Register developed by 30/06/2023 | 1 Asset Register developed by 30/06/2023 | 1Asset Register developed by 30/06/2024 | N/A | N/A | N/A | N/A | 1Asset Register developed by 30/06/2024 | N/A | N/A | N/A | N/A | N/A | N/A | Budget & Treasury Office | OPEX | Asset Register
MFVM13 |  |  | 72 | Date of adoption of Finance related policies by Council by 31/05/2024 | Date of adoption | n/a | Adoption of Finance related policies by Council 31/05/2023 | Adoption of Finance related policies by Council 31/05/2023 | Adoption of Finance related policies by Council 31/05/2024 | N/A | N/A | N/A | Adoption of Finance related policies by Council 31/05/2024 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Budget & Treasury Office | OPEX | Council Resolution
MFVM14 |  | Monitor the compliance with relevant legislation regarding financial expenditure | 73 | Percentage of reduction of Unauthorised, Irregular, Fruitless and Wasteful Expenditure by 30/06/2024 | Percentage of reduction | n/a | 10% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 30/06/2023 | 0% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 30/06/2023 | 10% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 30/06/2024 | 2% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 30/09/2023 | 0% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 30/09/2023 | 5% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 31/12/2024 | 8% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 30/06/2024 | 10% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 30/06/2024 | 0% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 31/12/2024 | 7% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 31/12/2024 | 0% reduction of unauthorised, irregular, fruitless and wasteful expenditure by 31/12/2024 | Not Achieved | The UIFW has not been written off by Council. The UIFW has been refered to MPAC for investigation | The Report will be tabled to Council on the 30 January 2024 | All Departments | OPEX | Signed Reports to Council
MFVM15 |  |  | 74 | Number of Unauthorised, Irregular, Fruitless and Wasteful Expenditure reports submitted to Council by 30/06/2024 | Number | n/a | 4 Unauthorised, Irregular, Fruitless and Wasteful Expenditure reports submitted to Council by 30/06/2023 | 4 Unauthorised, Irregular, Fruitless and Wasteful Expenditure reports submitted to Council by 30/06/2023 | 4 Unauthorised, Irregular, Fruitless and Wasteful Expenditure reports submitted to Council by 30/06/2024 | 1 Unauthorised, Irregular, Fruitless and Wasteful Expenditure report submitted to Council by 30/09/2023 | 1 Unauthorised, Irregular, Fruitless and Wasteful Expenditure report submitted to Council by 30/09/2023 | 1 Unauthorised, Irregular, Fruitless and Wasteful Expenditure report submitted to Council by 31/12/2023 | 1 Unauthorised, Irregular, Fruitless and Wasteful Expenditure report submitted to Council by 31/03/2024 | 1 Unauthorised, Irregular, Fruitless and Wasteful Expenditure report submitted to Council by 30/06/2024 | 1 Unauthorised, Irregular, Fruitless and Wasteful Expenditure report submitted to Council by 31/12/2023 | Two (2) Unauthorised, Irregular, Fruitless and Wasteful Expenditure report submitted to Council by 31/12/2023 | Two (2) Unauthorised, Irregular, Fruitless and Wasteful Expenditure report submitted to Council by 31/12/2023 | Achieved | N/A | N/A | All Departments | OPEX | Signed Reports to Council
MFVM16 | To improve audit opinion | Implement an audit action plan | 75 | Percentage of audit queries raised by the Auditor-General addressed by 30/06/2024 | Percentage of queries addressed | n/a | 100% of audit queries raised by the Auditor-General addressed by 30/06/2023 | 95% of of audit queries raised by the Auditor-General addressed by 30/06/2023 | 100% of audit queries raised by the Auditor-General addressed by 30/06/2024 | N/A | N/A | N/A | 75% of audit queries raised by the Auditor-General addressed by 31/03/2024 | 100% of audit queries raised by the Auditor-General addressed by 30/06/2024 | N/A | N/A | N/A | N/A | N/A | N/A | All Departments | OPEX | Audit action plan and dashboard report
KPA 6: CROSS CUTTING ISSUES
CCI01 | Efficient & Credible Stratgic & Spatial Municipal Planning | Revision of a Credible Intergrated Development Plan | 76 | Date of review and adoption of credible integrated development planning by Council by 31/05/2024 | Date of review and adoption | n/a | Review and adoption of credible integrated development planning by Council by 31/05/2023 | Reviewed and adopted credible integrated development planning on the 28/05/20221 | Review and adoption of credible integrated development planning by Council by 31/05/2024 | N/A | N/A | N/A | N/A | Review and adoption of credible integrated development planning by Council by 31/05/2024 | N/A | N/A | N/A | N/A | N/A | N/A | Office of the MM | OPEX | Council resolution and Integrated development plan
CCI02 | To ensure the implementation of Spatial Development Framework | Improved Spatial Development Framework | 77 | Date of review and adoption of district Spatial Development framework by Council by 30/06/2024 | Date of review and adoption | n/a | Review and adoption of district Spatial Development framework by Council by 30/06/2023 | Reviewed and adopted district Spatial Development framework by Council on the 28/05/2023 | Review and adoption of district Spatial Development framework by Council by 30/06/2024 | N/A | N/A | N/A | N/A | Review and adoption of district Spatial Development framework by Council by 30/06/2024 | N/A | N/A | N/A | N/A | N/A | N/A | Community Services | OPEX | Council resolution and Spatial Development framework
CCI03 | To ensure sustainable protection and development of the environment | Development and implementation of environmental management Plan | 78 | Date of review and adoption of Environmental Management Plan provided by Council by 30/06/2024 | Date of review and adoption | All | Date of review and adoption of Environmental Management Plan provided by Council by 30/06/2023 | Reviewed and Adopted Environmental Management Plan by Council by 28/05/2023 | Review and adoption of Environmental Management Plan provided by Council by 30/06/2024 | N/A | N/A | N/A | N/A | Review and adoption of Environmental Management Plan provided by Council by 30/06/2024 | N/A | N/A | N/A | N/A | N/A | N/A | Community Services | OPEX | Council Resolution and Environmental Management Plan
CCI04 | To create a safety and responsive environment to the community | Attending and responding to disasters and incidents with a district | 79 | Date of Submission of Disaster Management Annual Report on Disaster incidents in the prior year submitted to Council by 30 June 2024 | Date of submission | n/a | New Indicator | New Indicator | Submission of Disaster Management Annual Report on Disaster incidents in the prior year submitted to Council by 30 June 2024 | N/A | N/A | N/A | N/A | Submission of Disaster Management Annual Report on Disaster incidents in the prior year submitted to Council by 30 June 2024 | N/A | N/A | N/A | N/A | N/A | N/A | Community Services | OPEX | Disaster Management Annual Report,Council Resolution
CCI05 |  |  | 80 | Number Of Awareness Campaigns on Disaster provided to the UTDM Community by 30/06/2024 | Number of Awareness Campaigns | District -wide | New Indicator | New Indicator | Four (4)Awareness Campaigns on Disaster provided to the UTDM Community by 30/06/2024 | One (1)Awareness Campaigns on Disaster provided to the UTDM Community by 30/09/2023 | One (1)Awareness Campaigns on Disaster provided to the UTDM Community by 30/09/2023 | One (1)Awareness Campaigns on Disaster provided to the UTDM Community by 31/12/2023 | One (1)Awareness Campaigns on Disaster provided to the UTDM Community by 31/03/2024 | One (1)Awareness Campaigns on Disaster provided to the UTDM Community by 30/06/2024 | One (1)Awareness Campaigns on Disaster provided to the UTDM Community by 31/12/2023 | Two (2)Awareness Campaigns on Disaster provided to the UTDM Community by 31/12/2023 | Two (2)Awareness Campaigns on Disaster provided to the UTDM Community by 31/12/2023 | Achieved | N/A | N/A | Community Services | OPEX | Dated Report
CCI06 | To ensure proper communication with the public | Monitor the functioning and eficient of the Municipal Call Centre | 81 | Date of Review of the Call Centre Charter submitted to Council by 30/06/2024 | Date of review and adoption | n/a | New Indicator | New Indicator | Review of the UTDM Call Centre Charter submitted to Council by 30/06/2024 | N/A | N/A | N/A | N/A | Review of the UTDM Call Centre Charter submitted to Council by 30/06/2024 | N/A | N/A | N/A | N/A | N/A | N/A | Community Services | OPEX | Call Centre Charter,Council Resolution